## By journey
CJS journeys - who does what, 5 September 2026
Framework changes are made and pushed by the CJS team - pull and activate them. Handler and config work stays with the journey's own developer.
Journey | Service | Dept | Ticket | Blocks | Assignee | Obs | Closed | Open | FRAMEWORK - done by us, pull it | HANDLER CLASS - developer | CONFIG in the Studio - developer | BACKEND / PORTAL - other teams | NEEDS A LOOK
E021 | Alternative Fuel | EPDA | CJSMIG-683 | CJSMIG-468 | anand babu | 15 | 1 | 14 | 13. Feedback is mandatory | ZCL_EPDA_E021_ALTER_FUEL_LOGIC | 2. Applicant details not aligned - should be row wise -> Studio > Design tab. Place the applicant fields on one row of the 12-column grid (ZRAK_CJ_LAY). 4. Permit / EID / trade licence order wrong, no search button -> Field order in the Design tab; the search button appears when the field's FTYPE is SEARCH. 5. Company details field order not correct -> Design tab. 7. Grid: all row fields mandatory, drop the delete1 column -> REQUIRED per field, and remove the column from the grid spec in ZRAK_T_JNY_FLD-DEFAULT_VAL. 8. Units and No. of Months should be dropdowns -> Add the values to ZRAK_T_JNY_OPT and set CLOSED_LIST = X. 9. Supplier company: order and mandatory indicators -> Design tab + REQUIRED. 10. Step name 'Letter from the Supplier Company' -> 'Documents' -> Already coded in ZRAK_CJ_FIXPACK, English and Arabic. Run the report for this journey. 11. Mandatory attachment labels need the * indicator -> The engine draws the asterisk now - RENDER_ATTACH( ) passes the native required property. What is left is ticking REQUIRED on each upload field. 12. Declaration & Notes missing -> Add a DISPLAY field whose DEFAULT_VAL is TEXT:@nnn pointing at a ZRAK_T_CJ_TXT row, so it reads in both languages. | 6. Company name EN/AR not filled from the permit number 15. Arabic - service start button not showing | 1. Initial page loads with error messages -> The screenshot is already on the ticket, but Jira is not reachable from where this register is built - paste the error text here. Most likely the required-field messages firing before the citizen has typed anything, which is a rule/required config question, not the engine. 3. EPDA permit no & applicant type data missing -> The handler has no ON_INIT, so nothing seeds these. Confirm the field names in ZRAK_T_JNY_FLD and an ON_INIT can be written in an hour. 14. Case created (1959717) but attachments not saved -> Instrumented: ZCL_RAK_JOURNEY_BE now counts the files it could not read, says so on screen and names them on the trace. Re-run with &trace=x and send the ATTACH line.
E022 | Development Project | EPDA | CJSMIG-684 | CJSMIG-477 | anand babu | 15 | 1 | 14 | 13. Feedback is mandatory | ZCL_EPDA_E022_DEV_PROJ_LOGIC CODE READY - see the 'Handler code' sheet: 3. Applicant details are duplicated | 2. Applicant details not aligned - should be row wise -> Design tab. 4. Emirates ID search should follow the format; Browse not required -> PLACEHOLDER for the mask, REGEX for the format, FTYPE SEARCH instead of the browse control. 5. Permit / EID / trade licence order; permit number not a dropdown -> Design tab + FTYPE. 6. Company details field order not correct -> Design tab. 7. Company name English & Arabic duplicated -> Two fields are bound to the same value. Hide one in ZRAK_T_JNY_FLD. 8. Rename step 'Development Project' -> 'Project Details' -> Coded in ZRAK_CJ_FIXPACK, EN + AR. 9. Rename step 'Trade license' -> 'Documents' -> Coded in ZRAK_CJ_FIXPACK, EN + AR. 10. Trade licence attachment is missing -> Add the upload field to the Documents step. 11. Declaration & Note missing -> DISPLAY field with a TEXT: default. 12. Step 5 request confirmation not required -> Coded in ZRAK_CJ_FIXPACK as STEP_OFF - reversible, sets ACTIVE blank. | 15. Customer action not working | 1. Initial page loads with error messages -> The screenshot is on the ticket; paste it here - Jira is not reachable from where this register is built. 14. Attachments are not saving -> Re-run with &trace=x and send the ATTACH line.
D012 | School Trips & Activities | DOK | CJSMIG-685 | CJSMIG-351 | Jyoti Meena | 9 | 4 | 5 | - | ZCL_D012_SCHOOL_TRIP_ACT_LOGIC | - | 2. Selected Indian school, a different school reached the case 4. Customer Action from landing page, Upload does nothing 5. Cases not translated into Arabic 6. No case exists to submit in Arabic 7. Back button does not work to submit a new case | -
E017 | Export Chemical Products | EPDA | CJSMIG-687 | CJSMIG-522 | Jyoti Meena | 18 | 3 | 15 | 5. Mandatory-field message shows on the main screen, not in the dialog 6. One field per row - should be two or more 15. Feedback is mandatory | ZCL_E017_NOC_EXP_CHEM_LOGIC CODE READY - see the 'Handler code' sheet: 2. Representative + owner EID search errors and will not move to the next step 4. Add Chemical - all fields should be mandatory | 1. Owner search should be in EID format; Browse not required -> PLACEHOLDER + REGEX; FTYPE SEARCH. Listed in the fixpack worklist. 3. Permit number / trade licence etc. not required on the chemical tab -> Coded in ZRAK_CJ_FIXPACK as three HIDE rules anchored on the CHEMICALS_DETAILS grid. 8. 'Use a previous declaration' field not required -> Hide the field. 9. HS code should be a guided formatted number with a watermark -> REGEX for the format, PLACEHOLDER for the watermark. 12. 'up to 2 MB' repeats on every attachment; mandatory indicator missing -> The asterisk is engine-side and done; the repeated size hint is per-field wording. 13. Preview page should be removed -> Coded in ZRAK_CJ_FIXPACK as STEP_OFF. 14. Step 5 request confirmation not required -> Coded in ZRAK_CJ_FIXPACK as STEP_OFF. | 18. Chemical details missing in the backend 17. Customer action not working | 7. Bill of Lading input clears its own value -> Check BOL_POP actually exists in ZRAK_T_JNY_FLD - a field name that is not on the journey accepts set_val and get_val and does nothing. 10. Modify - existing values are not showing -> The edit path does not load the row back into the dialog. Needs a run. 11. Search from History is missing -> A real gap, not a bug: the legacy control reads ChemicalHistorySet on zega_fw_fnd_srv and no CJS class calls it. Needs a decision before it can be built. 16. Attachments are not saving -> Re-run with &trace=x.
D002 | Private School Licence - Apply | DOK | CJSMIG-688 | CJSMIG-252 | Hasan Fraz | 11 | 6 | 5 | - | ZCL_D002_SCHOOL_LIC_NEW_LOGIC | 6. Arabic translation not complete -> Handed to anand on the thread. ZLABEL_AR across the journey. 11. Mandatory attachments need the * -> Engine draws it; tick REQUIRED on each upload field. | 8. Manager empty in the application form 9. Cannot access Manager & School in the record model 10. Customer Action should redirect to the new CJS | -
D013 | Staff Appointment Letters | DOK | CJSMIG-689 | CJSMIG-360 | Jyoti Meena | 10 | 3 | 7 | - | ZCL_D013_STAFF_APP_LET_LOGIC | - | 1. Application form - data missing 3. Selected school is not the school on the case 10. Beneficiary not reflected in the record model - case stuck 4. Customer Action upload not working 5. Cases not translated into Arabic 6. No case exists to submit in Arabic 7. Back button does not work to submit a new case | -
D014 | Staff Experience Certificates | DOK | CJSMIG-690 | CJSMIG-369 | Jyoti Meena | 11 | 0 | 11 | - | ZCL_D014_STAFF_EXP_CERT_LOGIC (and ZCL_D014_STAFF_GOLD_VISA_LOGIC - two classes claim D014) | - | 2. Application form - data missing 3. Beneficiary not reflected in the record model - case stuck 4. Cannot complete the case - problem with the case output 5. Selected school is not the school on the case 6. Customer Action upload not working 7. Old case journey portal not working, cannot compare 8. Cases not translated into Arabic 9. No case exists to submit in Arabic 10. Back button does not work to submit a new case | 1. The service does not work on the portal screen -> Check which handler class the journey row points at first - two classes claim D014. 11. Cannot post payment through the landing page -> Run with &trace=x: PREPARE_PAYMENT( ) names its exit - NOCASE, NOSCREEN or NOURL - which says whether the case, the screen mapping or the gateway address is missing.
D003 | Private School Licence - Renew | DOK | CJSMIG-692 | CJSMIG-261 | anand babu | 5 | 0 | 5 | - | ZCL_D003_SCHOOL_LIC_RNEW_LOGIC | 1. Owner - BP labels missing -> Fill ZLABEL / ZLABEL_AR. In the fixpack worklist. 5. Mandatory attachments need the * -> Tick REQUIRED on each upload field. | 2. Owner details missing from the application form 3. Arabic version has no Start button 4. Customer Action should redirect to CJS | -
D021 | School Fees (Amend or Increase) | DOK | CJSMIG-693 | CJSMIG-396 | anand babu | 4 | 0 | 4 | - | ZCL_D021_MOD_SCHOOL_FEE_LOGIC | 1. Field should read Distance, not Educational stage -> ZLABEL / ZLABEL_AR. In the fixpack worklist - the field name is not known from here. | 2. Table should show every educational stage and fetch the current fee 3. Transportation fees do not reflect the distance - error, cannot submit 4. Cannot complete the case on the submission screen | -
D016 | Private School Licence - Cancel | DOK | CJSMIG-694 | CJSMIG-270 | anand babu | 3 | 0 | 3 | - | ZCL_D016_SCHOOL_LIC_CANC_LOGIC | 2. Mandatory attachments need the * -> Tick REQUIRED on each upload field. | 1. Arabic version has no Start button 3. Customer Action should redirect to CJS | -
D006 | Amend - Manage Change | DOK | CJSMIG-696 | CJSMIG-297 | Hasan Fraz | 4 | 0 | 4 | - | ZCL_D006_SCHOOL_MNG_CHG_LOGIC | 3. Mandatory attachments need the * -> Tick REQUIRED on each upload field. | 1. New manager details not shown on the application form 2. Arabic version has no Start button 4. Customer Action should redirect to CJS | -
E018 | Transport of Chemical Products | EPDA | CJSMIG-697 | CJSMIG-531 | Hasan Fraz | 10 | 2 | 8 | 5. Mandatory-field message shows on the main screen, not in the dialog 6. One field per row - should be two or more | ZCL_E018_NOC_TRANS_CHEM_LOGIC CODE READY - see the 'Handler code' sheet: 2. Representative + owner EID search errors and will not move on 4. Add Chemical - all fields should be mandatory 10. Backend POST failed - CX_SY_CONVERSION_NO_NUMBER, cannot go to the next step | 1. Owner search should be in EID format; Browse not required -> PLACEHOLDER + REGEX; FTYPE SEARCH. In the fixpack worklist. 3. Permit number / trade licence etc. not required on the chemical tab -> Coded in ZRAK_CJ_FIXPACK as three HIDE rules. 8. 'Use a previous declaration' field not required -> Hide the field. 9. HS code should be a guided formatted number with a watermark -> REGEX + PLACEHOLDER. | - | 7. Bill of Lading input clears its own value -> Check BOL_POP exists in ZRAK_T_JNY_FLD.
D005 | Amend - Name Change | DOK | CJSMIG-698 | CJSMIG-288 | Hasan Fraz | 3 | 0 | 3 | - | ZCL_D005_SCHOOL_NAME_CHG_LOGIC | 2. Mandatory attachments need the * -> Tick REQUIRED on each upload field. | 1. Arabic version has no Start button 3. Customer Action should redirect to the new CJS | -
D022 | Pursuing of Study Certificate | DOK | CJSMIG-699 | CJSMIG-405 | Hasan Fraz | 5 | 2 | 3 | - | ZCL_D022_STUD_STUDY_CERT_LOGIC | - | 1. Service card is missing the 'who can apply' information | 4. The payment step errors when paying -> Run with &trace=x. PREPARE_PAYMENT( ) reports its exit and the keys the backend answered with, which separates 'no case' from 'no gateway address'. 5. Cannot complete the case at the payment step -> Blocker - same run as above.
E019 | Transport of Used Oil | EPDA | CJSMIG-700 | CJSMIG-540 | anand babu | 23 | 1 | 22 | 18. Feedback is mandatory | ZCL_EPDA_E019_TRANS_USED_LOGIC | 2. Applicant details not aligned - should be row wise -> Design tab. 3. Applicant details are duplicated -> Not the same cause as E022 - this handler writes nothing. Two fields are bound to the same value; hide one. 4. Emirates ID search should follow the format; Browse not required -> PLACEHOLDER + REGEX; FTYPE SEARCH. 5. Permit / EID / trade licence order; permit number not a dropdown -> Design tab + FTYPE. 6. Company details field order not correct -> Design tab. 7. Company name English & Arabic duplicated -> Hide one of the two fields. 8. 'Material Text 1' should read 'Name' -> ZLABEL / ZLABEL_AR. 9. Issuing emirates should be a dropdown -> ZRAK_T_JNY_OPT + CLOSED_LIST. 10. Vehicle Code must not allow more than 2 digits -> MAX_LEN on the field. 11. Vehicle Plate must not allow more than 4 digits -> MAX_LEN on the field. 12. Remove the 'Mtable Delete 2' column -> Drop it from the grid spec in DEFAULT_VAL. 13. Units should be a dropdown -> ZRAK_T_JNY_OPT + CLOSED_LIST. 14. Address, Registered Emirate, Trade Licence should be inputs, not display -> Change FTYPE from DISPLAY to INPUT and tick REQUIRED. 15. Step name should change to Documents -> Step title, EN + AR. 16. Mandatory attachments need the * -> Tick REQUIRED on each upload field. 17. Declaration & Notes missing -> DISPLAY field with a TEXT: default. | 20. Company name not updated in the backend 21. UOM not updated in the backend 22. Customer action 23. Arabic services cannot be submitted | 1. Initial page loads with error messages -> The screenshot is on the ticket; paste it here - Jira is not reachable from where this register is built. 19. Attachments are not saving -> Re-run with &trace=x.
E020 | Batteries / Scrap Handling | EPDA | CJSMIG-701 | CJSMIG-549 | Hasan Fraz | 14 | 1 | 13 | 12. Feedback is mandatory | ZCL_EPDA_E020_BATT_SCRAP_LOGIC | 2. Applicant details not aligned - should be row wise -> Design tab. 3. Applicant details are duplicated -> Two fields bound to the same value; hide one. 4. Emirates ID search should follow the format; Browse not required -> PLACEHOLDER + REGEX; FTYPE SEARCH. 5. Permit / EID / trade licence order; permit number not a dropdown -> Design tab + FTYPE. 6. Rename the step 'Material Origin source' to 'Batteries/Scrap Details' -> Step title, EN + AR. 7. Fields under Material origin source must be dynamic and mandatory by dropdown value -> Show/hide belongs in ZRAK_T_JNY_RULE keyed on the dropdown, with REQUIRED on the fields it reveals. 8. Vehicle code 1 digit, vehicle plate 4 digits -> MAX_LEN on both fields. 9. 'Materials Det' is duplicated and should be renamed -> Hide one, rename the other. 10. Declaration & Note missing -> DISPLAY field with a TEXT: default. 11. Step 5 request confirmation not required -> STEP_OFF - the fixpack does this for other journeys and takes one more line. | 14. Vehicle details not saving in the backend | 1. Initial page loads with error messages -> The screenshot is on the ticket; paste it here - Jira is not reachable from where this register is built. 13. Attachments are not saving -> Re-run with &trace=x.
E023 | Dewatering Approval | EPDA | CJSMIG-702 | CJSMIG-558 | anand babu | 1 | 0 | 1 | - | ZCL_E023_DEWATERING_LOGIC | 1. CJS service Not found -> The handler class exists and is complete. Check the ZRAK_T_JNY row and the launch URL's journey id - a code that does not resolve gives exactly this. | - | -
E025 | Beekeeping Activity | EPDA | CJSMIG-703 | CJSMIG-567 | anand babu | 6 | 0 | 6 | - | ZCL_E025_BEEKEEPING_LOGIC CODE READY - see the 'Handler code' sheet: 6. Applicant BP not saved in the record model, not in the backend application | 1. Emirates ID search should follow the format; Browse not required -> PLACEHOLDER + REGEX; FTYPE SEARCH. 2. Number of Apiaries max 2 digits; Expected Production max 6 -> MAX_LEN on both fields. 3. Mandatory attachments need the * -> Tick REQUIRED on each upload field. 4. Declaration & Note missing -> DISPLAY field with a TEXT: default. | - | 5. Case id is not correct - shows the wrong number -> Send the number that was shown next to the case it belongs to. On some families the journey key is not the case id, and the engine has one resolver for that - but it needs the pair to confirm.
E026 | Tree Removal / Relocation / Pruning | EPDA | CJSMIG-704 | CJSMIG-576 | anand babu | 5 | 0 | 5 | - | ZCL_E026_TREE_REMOVAL_LOGIC CODE READY - see the 'Handler code' sheet: 5. Applicant BP not saved in the record model, not in the backend application | 1. Emirates ID search should follow the format; Browse not required -> PLACEHOLDER + REGEX; FTYPE SEARCH. 2. Mandatory attachments need the * -> Tick REQUIRED on each upload field. 3. Declaration & Note missing -> DISPLAY field with a TEXT: default. | - | 4. Case id is not correct - shows the wrong number -> Same as E025 - send the pair of numbers.

## All observations
Journey | Service | Ticket | # | Observation | Who does it | Bucket | What closes it
E021 | Alternative Fuel | CJSMIG-683 | 1 | Initial page loads with error messages | Reporter + developer | Needs a look | The screenshot is already on the ticket, but Jira is not reachable from where this register is built - paste the error text here. Most likely the required-field messages firing before the citizen has typed anything, which is a rule/required config question, not the engine.
E021 | Alternative Fuel | CJSMIG-683 | 2 | Applicant details not aligned - should be row wise | Journey developer - Studio config | Config - developer | Studio > Design tab. Place the applicant fields on one row of the 12-column grid (ZRAK_CJ_LAY).
E021 | Alternative Fuel | CJSMIG-683 | 3 | EPDA permit no & applicant type data missing | Reporter + developer | Needs a look | The handler has no ON_INIT, so nothing seeds these. Confirm the field names in ZRAK_T_JNY_FLD and an ON_INIT can be written in an hour.
E021 | Alternative Fuel | CJSMIG-683 | 4 | Permit / EID / trade licence order wrong, no search button | Journey developer - Studio config | Config - developer | Field order in the Design tab; the search button appears when the field's FTYPE is SEARCH.
E021 | Alternative Fuel | CJSMIG-683 | 5 | Company details field order not correct | Journey developer - Studio config | Config - developer | Design tab.
E021 | Alternative Fuel | CJSMIG-683 | 6 | Company name EN/AR not filled from the permit number | Backend team | Backend / record model | The permit read has to return the company name. Backend/BAdI.
E021 | Alternative Fuel | CJSMIG-683 | 7 | Grid: all row fields mandatory, drop the delete1 column | Journey developer - Studio config | Config - developer | REQUIRED per field, and remove the column from the grid spec in ZRAK_T_JNY_FLD-DEFAULT_VAL.
E021 | Alternative Fuel | CJSMIG-683 | 8 | Units and No. of Months should be dropdowns | Journey developer - Studio config | Config - developer | Add the values to ZRAK_T_JNY_OPT and set CLOSED_LIST = X.
E021 | Alternative Fuel | CJSMIG-683 | 9 | Supplier company: order and mandatory indicators | Journey developer - Studio config | Config - developer | Design tab + REQUIRED.
E021 | Alternative Fuel | CJSMIG-683 | 10 | Step name 'Letter from the Supplier Company' -> 'Documents' | Journey developer - Studio config | Config - developer | Already coded in ZRAK_CJ_FIXPACK, English and Arabic. Run the report for this journey.
E021 | Alternative Fuel | CJSMIG-683 | 11 | Mandatory attachment labels need the * indicator | Journey developer - Studio config | Config - developer | The engine draws the asterisk now - RENDER_ATTACH( ) passes the native required property. What is left is ticking REQUIRED on each upload field.
E021 | Alternative Fuel | CJSMIG-683 | 12 | Declaration & Notes missing | Journey developer - Studio config | Config - developer | Add a DISPLAY field whose DEFAULT_VAL is TEXT:@nnn pointing at a ZRAK_T_CJ_TXT row, so it reads in both languages.
E021 | Alternative Fuel | CJSMIG-683 | 13 | Feedback is mandatory | Framework team (us) | Framework - we push | A 'Not now' button now sits beside Send feedback and the journey finishes without it. ZCL_RAK_JOURNEY_RENDER + ZCL_RAK_JOURNEY_ENGINE (FBSKIP).
E021 | Alternative Fuel | CJSMIG-683 | 14 | Case created (1959717) but attachments not saved | Reporter + developer | Needs a look | Instrumented: ZCL_RAK_JOURNEY_BE now counts the files it could not read, says so on screen and names them on the trace. Re-run with &trace=x and send the ATTACH line.
E021 | Alternative Fuel | CJSMIG-683 | 15 | Arabic - service start button not showing | Portal team | Portal / launchpad | Service card / launchpad, not CJS.
E022 | Development Project | CJSMIG-684 | 1 | Initial page loads with error messages | Reporter + developer | Needs a look | The screenshot is on the ticket; paste it here - Jira is not reachable from where this register is built.
E022 | Development Project | CJSMIG-684 | 2 | Applicant details not aligned - should be row wise | Journey developer - Studio config | Config - developer | Design tab.
E022 | Development Project | CJSMIG-684 | 3 | Applicant details are duplicated | Journey developer - ABAP | Handler class - developer | The handler was writing the applicant fields twice. Fixed in ZCL_EPDA_E022_DEV_PROJ_LOGIC.
E022 | Development Project | CJSMIG-684 | 4 | Emirates ID search should follow the format; Browse not required | Journey developer - Studio config | Config - developer | PLACEHOLDER for the mask, REGEX for the format, FTYPE SEARCH instead of the browse control.
E022 | Development Project | CJSMIG-684 | 5 | Permit / EID / trade licence order; permit number not a dropdown | Journey developer - Studio config | Config - developer | Design tab + FTYPE.
E022 | Development Project | CJSMIG-684 | 6 | Company details field order not correct | Journey developer - Studio config | Config - developer | Design tab.
E022 | Development Project | CJSMIG-684 | 7 | Company name English & Arabic duplicated | Journey developer - Studio config | Config - developer | Two fields are bound to the same value. Hide one in ZRAK_T_JNY_FLD.
E022 | Development Project | CJSMIG-684 | 8 | Rename step 'Development Project' -> 'Project Details' | Journey developer - Studio config | Config - developer | Coded in ZRAK_CJ_FIXPACK, EN + AR.
E022 | Development Project | CJSMIG-684 | 9 | Rename step 'Trade license' -> 'Documents' | Journey developer - Studio config | Config - developer | Coded in ZRAK_CJ_FIXPACK, EN + AR.
E022 | Development Project | CJSMIG-684 | 10 | Trade licence attachment is missing | Journey developer - Studio config | Config - developer | Add the upload field to the Documents step.
E022 | Development Project | CJSMIG-684 | 11 | Declaration & Note missing | Journey developer - Studio config | Config - developer | DISPLAY field with a TEXT: default.
E022 | Development Project | CJSMIG-684 | 12 | Step 5 request confirmation not required | Journey developer - Studio config | Config - developer | Coded in ZRAK_CJ_FIXPACK as STEP_OFF - reversible, sets ACTIVE blank.
E022 | Development Project | CJSMIG-684 | 13 | Feedback is mandatory | Framework team (us) | Framework - we push | 'Not now' button - same engine fix as E021.
E022 | Development Project | CJSMIG-684 | 14 | Attachments are not saving | Reporter + developer | Needs a look | Re-run with &trace=x and send the ATTACH line.
E022 | Development Project | CJSMIG-684 | 15 | Customer action not working | Portal team | Portal / launchpad | Landing page redirect - portal team.
D012 | School Trips & Activities | CJSMIG-685 | 1 | Attachment types should allow JPG, PNG etc | Journey developer - closed | Closed by developer | Closed by Jyoti.
D012 | School Trips & Activities | CJSMIG-685 | 2 | Selected Indian school, a different school reached the case | Backend team | Backend / record model | Backend data mapping - Jyoti's own answer.
D012 | School Trips & Activities | CJSMIG-685 | 3 | Attachments not reflected into the case | Journey developer - closed | Closed by developer | Closed by Jyoti.
D012 | School Trips & Activities | CJSMIG-685 | 4 | Customer Action from landing page, Upload does nothing | Portal team | Portal / launchpad | Framework side - Jyoti's answer.
D012 | School Trips & Activities | CJSMIG-685 | 5 | Cases not translated into Arabic | Portal team | Portal / launchpad | Framework side.
D012 | School Trips & Activities | CJSMIG-685 | 6 | No case exists to submit in Arabic | Portal team | Portal / launchpad | Framework side.
D012 | School Trips & Activities | CJSMIG-685 | 7 | Back button does not work to submit a new case | Portal team | Portal / launchpad | Framework side.
D012 | School Trips & Activities | CJSMIG-685 | 8 | Applicant type field alignment | Journey developer - closed | Closed by developer | Closed by Jyoti.
D012 | School Trips & Activities | CJSMIG-685 | 9 | Curriculum type field alignment | Journey developer - closed | Closed by developer | Closed by Jyoti.
E017 | Export Chemical Products | CJSMIG-687 | 1 | Owner search should be in EID format; Browse not required | Journey developer - Studio config | Config - developer | PLACEHOLDER + REGEX; FTYPE SEARCH. Listed in the fixpack worklist.
E017 | Export Chemical Products | CJSMIG-687 | 2 | Representative + owner EID search errors and will not move to the next step | Journey developer - ABAP | Handler class - developer | Fix written - see the Handler code sheet. ON_CUSTOM_VALIDATE refused step 0 whenever APPLICANT_ROLE was set and its projected flags PARTNER_OWNER / PARTNER_REP were not. Those flags are only written by ON_CHANGE, so a BP search coming back left the pair inconsistent, and re-selecting the same value raises no CHANGE - so the one instruction the message gave could not clear it. It re-derives now instead of refusing.
E017 | Export Chemical Products | CJSMIG-687 | 3 | Permit number / trade licence etc. not required on the chemical tab | Journey developer - Studio config | Config - developer | Coded in ZRAK_CJ_FIXPACK as three HIDE rules anchored on the CHEMICALS_DETAILS grid.
E017 | Export Chemical Products | CJSMIG-687 | 4 | Add Chemical - all fields should be mandatory | Journey developer - ABAP | Handler class - developer | All fourteen are now marked with an asterisk and enforced. Ten of the fourteen checks had been commented out. ZCL_E017_NOC_EXP_CHEM_LOGIC->VALIDATE_INPUT( ).
E017 | Export Chemical Products | CJSMIG-687 | 5 | Mandatory-field message shows on the main screen, not in the dialog | Framework team (us) | Framework - we push | DIALOG_FORM( ) now draws pending messages inside the dialog. ZCL_RAK_JOURNEY_LOGIC.
E017 | Export Chemical Products | CJSMIG-687 | 6 | One field per row - should be two or more | Framework team (us) | Framework - we push | Popup dialogs lay out in two columns now. The fix was FormContainers, not the columnsL property. ZCL_RAK_JOURNEY_LOGIC->DIALOG_FORM( ).
E017 | Export Chemical Products | CJSMIG-687 | 7 | Bill of Lading input clears its own value | Reporter + developer | Needs a look | Check BOL_POP actually exists in ZRAK_T_JNY_FLD - a field name that is not on the journey accepts set_val and get_val and does nothing.
E017 | Export Chemical Products | CJSMIG-687 | 8 | 'Use a previous declaration' field not required | Journey developer - Studio config | Config - developer | Hide the field.
E017 | Export Chemical Products | CJSMIG-687 | 9 | HS code should be a guided formatted number with a watermark | Journey developer - Studio config | Config - developer | REGEX for the format, PLACEHOLDER for the watermark.
E017 | Export Chemical Products | CJSMIG-687 | 10 | Modify - existing values are not showing | Reporter + developer | Needs a look | The edit path does not load the row back into the dialog. Needs a run.
E017 | Export Chemical Products | CJSMIG-687 | 11 | Search from History is missing | Reporter + developer | Needs a look | A real gap, not a bug: the legacy control reads ChemicalHistorySet on zega_fw_fnd_srv and no CJS class calls it. Needs a decision before it can be built.
E017 | Export Chemical Products | CJSMIG-687 | 12 | 'up to 2 MB' repeats on every attachment; mandatory indicator missing | Journey developer - Studio config | Config - developer | The asterisk is engine-side and done; the repeated size hint is per-field wording.
E017 | Export Chemical Products | CJSMIG-687 | 13 | Preview page should be removed | Journey developer - Studio config | Config - developer | Coded in ZRAK_CJ_FIXPACK as STEP_OFF.
E017 | Export Chemical Products | CJSMIG-687 | 14 | Step 5 request confirmation not required | Journey developer - Studio config | Config - developer | Coded in ZRAK_CJ_FIXPACK as STEP_OFF.
E017 | Export Chemical Products | CJSMIG-687 | 15 | Feedback is mandatory | Framework team (us) | Framework - we push | 'Not now' button.
E017 | Export Chemical Products | CJSMIG-687 | 16 | Attachments are not saving | Reporter + developer | Needs a look | Re-run with &trace=x.
E017 | Export Chemical Products | CJSMIG-687 | 17 | Customer action not working | Portal team | Portal / launchpad | Portal team.
E017 | Export Chemical Products | CJSMIG-687 | 18 | Chemical details missing in the backend | Backend team | Backend / record model | Read the grid spec against the LIST_SEQUENCE rows for that screen in /QNV/SB_UI_DEFIN - a backend table's cells are positional at both ends.
D002 | Private School Licence - Apply | CJSMIG-688 | 1 | Add Manager - wrong text, should be Birthday | Journey developer - closed | Closed by developer | Closed by Hasan. Also coded in ZRAK_CJ_FIXPACK as a LABEL change on MANAGER_DOB.
D002 | Private School Licence - Apply | CJSMIG-688 | 2 | Fees Details comes back empty | Journey developer - closed | Closed by developer | Closed by Hasan.
D002 | Private School Licence - Apply | CJSMIG-688 | 3 | Building Information should be demit | Journey developer - closed | Closed by developer | Closed by Hasan.
D002 | Private School Licence - Apply | CJSMIG-688 | 4 | Attachment type shows DOC, should be PDF / JPG | Journey developer - closed | Closed by developer | Closed by Hasan. Also coded in ZRAK_CJ_FIXPACK as an ATTACH_TYPE change.
D002 | Private School Licence - Apply | CJSMIG-688 | 5 | Cannot upload a PDF or a photo | Journey developer - closed | Closed by developer | Closed by Hasan - same accept list.
D002 | Private School Licence - Apply | CJSMIG-688 | 6 | Arabic translation not complete | Journey developer - Studio config | Config - developer | Handed to anand on the thread. ZLABEL_AR across the journey.
D002 | Private School Licence - Apply | CJSMIG-688 | 7 | Attachments not reflected to the record model | Journey developer - closed | Closed by developer | Closed by Hasan.
D002 | Private School Licence - Apply | CJSMIG-688 | 8 | Manager empty in the application form | Backend team | Backend / record model | Not answered on the thread. Record model.
D002 | Private School Licence - Apply | CJSMIG-688 | 9 | Cannot access Manager & School in the record model | Backend team | Backend / record model | Handed to anand on the thread.
D002 | Private School Licence - Apply | CJSMIG-688 | 10 | Customer Action should redirect to the new CJS | Portal team | Portal / launchpad | Portal team.
D002 | Private School Licence - Apply | CJSMIG-688 | 11 | Mandatory attachments need the * | Journey developer - Studio config | Config - developer | Engine draws it; tick REQUIRED on each upload field.
D013 | Staff Appointment Letters | CJSMIG-689 | 1 | Application form - data missing | Backend team | Backend / record model | Record model.
D013 | Staff Appointment Letters | CJSMIG-689 | 2 | Only one attachment reflected, the others not | Journey developer - closed | Closed by developer | Closed by Jyoti. Worth knowing why: GET_ATTACHMENT( ) de-duplicates on (objsrc, diffcrt, objsrctype, objtrgtype), so two files sharing a document type collapse into one.
D013 | Staff Appointment Letters | CJSMIG-689 | 3 | Selected school is not the school on the case | Backend team | Backend / record model | Backend data mapping - Jyoti's answer.
D013 | Staff Appointment Letters | CJSMIG-689 | 4 | Customer Action upload not working | Portal team | Portal / launchpad | Framework side - Jyoti's answer.
D013 | Staff Appointment Letters | CJSMIG-689 | 5 | Cases not translated into Arabic | Portal team | Portal / launchpad | Framework side.
D013 | Staff Appointment Letters | CJSMIG-689 | 6 | No case exists to submit in Arabic | Portal team | Portal / launchpad | Framework side.
D013 | Staff Appointment Letters | CJSMIG-689 | 7 | Back button does not work to submit a new case | Portal team | Portal / launchpad | Framework side.
D013 | Staff Appointment Letters | CJSMIG-689 | 8 | Applicant type field alignment | Journey developer - closed | Closed by developer | Closed by Jyoti.
D013 | Staff Appointment Letters | CJSMIG-689 | 9 | Remove the spaces on grades | Journey developer - closed | Closed by developer | Closed by Jyoti.
D013 | Staff Appointment Letters | CJSMIG-689 | 10 | Beneficiary not reflected in the record model - case stuck | Backend team | Backend / record model | anand to advise on the mapping - Jyoti's answer.
D014 | Staff Experience Certificates | CJSMIG-690 | 1 | The service does not work on the portal screen | Reporter + developer | Needs a look | Check which handler class the journey row points at first - two classes claim D014.
D014 | Staff Experience Certificates | CJSMIG-690 | 2 | Application form - data missing | Backend team | Backend / record model | Record model.
D014 | Staff Experience Certificates | CJSMIG-690 | 3 | Beneficiary not reflected in the record model - case stuck | Backend team | Backend / record model | Same fault as D013.
D014 | Staff Experience Certificates | CJSMIG-690 | 4 | Cannot complete the case - problem with the case output | Backend team | Backend / record model | Follows from the beneficiary fault.
D014 | Staff Experience Certificates | CJSMIG-690 | 5 | Selected school is not the school on the case | Backend team | Backend / record model | Backend data mapping.
D014 | Staff Experience Certificates | CJSMIG-690 | 6 | Customer Action upload not working | Portal team | Portal / launchpad | Framework side.
D014 | Staff Experience Certificates | CJSMIG-690 | 7 | Old case journey portal not working, cannot compare | Portal team | Portal / launchpad | Portal team.
D014 | Staff Experience Certificates | CJSMIG-690 | 8 | Cases not translated into Arabic | Portal team | Portal / launchpad | Framework side.
D014 | Staff Experience Certificates | CJSMIG-690 | 9 | No case exists to submit in Arabic | Portal team | Portal / launchpad | Framework side.
D014 | Staff Experience Certificates | CJSMIG-690 | 10 | Back button does not work to submit a new case | Portal team | Portal / launchpad | Framework side.
D014 | Staff Experience Certificates | CJSMIG-690 | 11 | Cannot post payment through the landing page | Reporter + developer | Needs a look | Run with &trace=x: PREPARE_PAYMENT( ) names its exit - NOCASE, NOSCREEN or NOURL - which says whether the case, the screen mapping or the gateway address is missing.
D003 | Private School Licence - Renew | CJSMIG-692 | 1 | Owner - BP labels missing | Journey developer - Studio config | Config - developer | Fill ZLABEL / ZLABEL_AR. In the fixpack worklist.
D003 | Private School Licence - Renew | CJSMIG-692 | 2 | Owner details missing from the application form | Backend team | Backend / record model | Record model.
D003 | Private School Licence - Renew | CJSMIG-692 | 3 | Arabic version has no Start button | Portal team | Portal / launchpad | Service card.
D003 | Private School Licence - Renew | CJSMIG-692 | 4 | Customer Action should redirect to CJS | Portal team | Portal / launchpad | Portal team.
D003 | Private School Licence - Renew | CJSMIG-692 | 5 | Mandatory attachments need the * | Journey developer - Studio config | Config - developer | Tick REQUIRED on each upload field.
D021 | School Fees (Amend or Increase) | CJSMIG-693 | 1 | Field should read Distance, not Educational stage | Journey developer - Studio config | Config - developer | ZLABEL / ZLABEL_AR. In the fixpack worklist - the field name is not known from here.
D021 | School Fees (Amend or Increase) | CJSMIG-693 | 2 | Table should show every educational stage and fetch the current fee | Backend team | Backend / record model | The read has to return all stages with their current fee.
D021 | School Fees (Amend or Increase) | CJSMIG-693 | 3 | Transportation fees do not reflect the distance - error, cannot submit | Backend team | Backend / record model | Blocker. The distance is not coming back from the system; the submit fails on it.
D021 | School Fees (Amend or Increase) | CJSMIG-693 | 4 | Cannot complete the case on the submission screen | Backend team | Backend / record model | Follows from the fee fault above.
D016 | Private School Licence - Cancel | CJSMIG-694 | 1 | Arabic version has no Start button | Portal team | Portal / launchpad | Service card. Reassigned to anand.
D016 | Private School Licence - Cancel | CJSMIG-694 | 2 | Mandatory attachments need the * | Journey developer - Studio config | Config - developer | Tick REQUIRED on each upload field.
D016 | Private School Licence - Cancel | CJSMIG-694 | 3 | Customer Action should redirect to CJS | Portal team | Portal / launchpad | Portal team.
D006 | Amend - Manage Change | CJSMIG-696 | 1 | New manager details not shown on the application form | Backend team | Backend / record model | Record model.
D006 | Amend - Manage Change | CJSMIG-696 | 2 | Arabic version has no Start button | Portal team | Portal / launchpad | Service card.
D006 | Amend - Manage Change | CJSMIG-696 | 3 | Mandatory attachments need the * | Journey developer - Studio config | Config - developer | Tick REQUIRED on each upload field.
D006 | Amend - Manage Change | CJSMIG-696 | 4 | Customer Action should redirect to CJS | Portal team | Portal / launchpad | Portal team.
E018 | Transport of Chemical Products | CJSMIG-697 | 1 | Owner search should be in EID format; Browse not required | Journey developer - Studio config | Config - developer | PLACEHOLDER + REGEX; FTYPE SEARCH. In the fixpack worklist.
E018 | Transport of Chemical Products | CJSMIG-697 | 2 | Representative + owner EID search errors and will not move on | Journey developer - ABAP | Handler class - developer | Same fix as E017 - ON_CUSTOM_VALIDATE re-derives the role flags instead of refusing the step. Re-test after the class is activated, since it had no active version.
E018 | Transport of Chemical Products | CJSMIG-697 | 3 | Permit number / trade licence etc. not required on the chemical tab | Journey developer - Studio config | Config - developer | Coded in ZRAK_CJ_FIXPACK as three HIDE rules.
E018 | Transport of Chemical Products | CJSMIG-697 | 4 | Add Chemical - all fields should be mandatory | Journey developer - ABAP | Handler class - developer | All fourteen marked and enforced. ZCL_E018_NOC_TRANS_CHEM_LOGIC.
E018 | Transport of Chemical Products | CJSMIG-697 | 5 | Mandatory-field message shows on the main screen, not in the dialog | Framework team (us) | Framework - we push | Engine fix - messages now draw inside the dialog.
E018 | Transport of Chemical Products | CJSMIG-697 | 6 | One field per row - should be two or more | Framework team (us) | Framework - we push | Two-column dialogs - engine fix.
E018 | Transport of Chemical Products | CJSMIG-697 | 7 | Bill of Lading input clears its own value | Reporter + developer | Needs a look | Check BOL_POP exists in ZRAK_T_JNY_FLD.
E018 | Transport of Chemical Products | CJSMIG-697 | 8 | 'Use a previous declaration' field not required | Journey developer - Studio config | Config - developer | Hide the field.
E018 | Transport of Chemical Products | CJSMIG-697 | 9 | HS code should be a guided formatted number with a watermark | Journey developer - Studio config | Config - developer | REGEX + PLACEHOLDER.
E018 | Transport of Chemical Products | CJSMIG-697 | 10 | Backend POST failed - CX_SY_CONVERSION_NO_NUMBER, cannot go to the next step | Journey developer - ABAP | Handler class - developer | The class had no active version at all - a CONSTANTS ... TYPE string VALUE '' will not compile - so SAP was running an older build of every method on this journey. The one-line correction is on the Handler code sheet. Fix it, activate, and re-test this line first.
D005 | Amend - Name Change | CJSMIG-698 | 1 | Arabic version has no Start button | Portal team | Portal / launchpad | Service card.
D005 | Amend - Name Change | CJSMIG-698 | 2 | Mandatory attachments need the * | Journey developer - Studio config | Config - developer | Tick REQUIRED on each upload field.
D005 | Amend - Name Change | CJSMIG-698 | 3 | Customer Action should redirect to the new CJS | Portal team | Portal / launchpad | Portal team.
D022 | Pursuing of Study Certificate | CJSMIG-699 | 1 | Service card is missing the 'who can apply' information | Portal team | Portal / launchpad | Service catalogue - taken by Vikram on the thread.
D022 | Pursuing of Study Certificate | CJSMIG-699 | 2 | Cannot search by Emirates ID; the field stays on SIS ID | Journey developer - closed | Closed by developer | Closed by Hasan - the Emirates ID option was removed, SIS ID only.
D022 | Pursuing of Study Certificate | CJSMIG-699 | 3 | Academic Year / School and Terms do not match the old version | Journey developer - closed | Closed by developer | Closed by Hasan - both removed.
D022 | Pursuing of Study Certificate | CJSMIG-699 | 4 | The payment step errors when paying | Reporter + developer | Needs a look | Run with &trace=x. PREPARE_PAYMENT( ) reports its exit and the keys the backend answered with, which separates 'no case' from 'no gateway address'.
D022 | Pursuing of Study Certificate | CJSMIG-699 | 5 | Cannot complete the case at the payment step | Reporter + developer | Needs a look | Blocker - same run as above.
E019 | Transport of Used Oil | CJSMIG-700 | 1 | Initial page loads with error messages | Reporter + developer | Needs a look | The screenshot is on the ticket; paste it here - Jira is not reachable from where this register is built.
E019 | Transport of Used Oil | CJSMIG-700 | 2 | Applicant details not aligned - should be row wise | Journey developer - Studio config | Config - developer | Design tab.
E019 | Transport of Used Oil | CJSMIG-700 | 3 | Applicant details are duplicated | Journey developer - Studio config | Config - developer | Not the same cause as E022 - this handler writes nothing. Two fields are bound to the same value; hide one.
E019 | Transport of Used Oil | CJSMIG-700 | 4 | Emirates ID search should follow the format; Browse not required | Journey developer - Studio config | Config - developer | PLACEHOLDER + REGEX; FTYPE SEARCH.
E019 | Transport of Used Oil | CJSMIG-700 | 5 | Permit / EID / trade licence order; permit number not a dropdown | Journey developer - Studio config | Config - developer | Design tab + FTYPE.
E019 | Transport of Used Oil | CJSMIG-700 | 6 | Company details field order not correct | Journey developer - Studio config | Config - developer | Design tab.
E019 | Transport of Used Oil | CJSMIG-700 | 7 | Company name English & Arabic duplicated | Journey developer - Studio config | Config - developer | Hide one of the two fields.
E019 | Transport of Used Oil | CJSMIG-700 | 8 | 'Material Text 1' should read 'Name' | Journey developer - Studio config | Config - developer | ZLABEL / ZLABEL_AR.
E019 | Transport of Used Oil | CJSMIG-700 | 9 | Issuing emirates should be a dropdown | Journey developer - Studio config | Config - developer | ZRAK_T_JNY_OPT + CLOSED_LIST.
E019 | Transport of Used Oil | CJSMIG-700 | 10 | Vehicle Code must not allow more than 2 digits | Journey developer - Studio config | Config - developer | MAX_LEN on the field.
E019 | Transport of Used Oil | CJSMIG-700 | 11 | Vehicle Plate must not allow more than 4 digits | Journey developer - Studio config | Config - developer | MAX_LEN on the field.
E019 | Transport of Used Oil | CJSMIG-700 | 12 | Remove the 'Mtable Delete 2' column | Journey developer - Studio config | Config - developer | Drop it from the grid spec in DEFAULT_VAL.
E019 | Transport of Used Oil | CJSMIG-700 | 13 | Units should be a dropdown | Journey developer - Studio config | Config - developer | ZRAK_T_JNY_OPT + CLOSED_LIST.
E019 | Transport of Used Oil | CJSMIG-700 | 14 | Address, Registered Emirate, Trade Licence should be inputs, not display | Journey developer - Studio config | Config - developer | Change FTYPE from DISPLAY to INPUT and tick REQUIRED.
E019 | Transport of Used Oil | CJSMIG-700 | 15 | Step name should change to Documents | Journey developer - Studio config | Config - developer | Step title, EN + AR.
E019 | Transport of Used Oil | CJSMIG-700 | 16 | Mandatory attachments need the * | Journey developer - Studio config | Config - developer | Tick REQUIRED on each upload field.
E019 | Transport of Used Oil | CJSMIG-700 | 17 | Declaration & Notes missing | Journey developer - Studio config | Config - developer | DISPLAY field with a TEXT: default.
E019 | Transport of Used Oil | CJSMIG-700 | 18 | Feedback is mandatory | Framework team (us) | Framework - we push | 'Not now' button.
E019 | Transport of Used Oil | CJSMIG-700 | 19 | Attachments are not saving | Reporter + developer | Needs a look | Re-run with &trace=x.
E019 | Transport of Used Oil | CJSMIG-700 | 20 | Company name not updated in the backend | Backend team | Backend / record model | Backend write.
E019 | Transport of Used Oil | CJSMIG-700 | 21 | UOM not updated in the backend | Backend team | Backend / record model | Backend write.
E019 | Transport of Used Oil | CJSMIG-700 | 22 | Customer action | Portal team | Portal / launchpad | Portal team.
E019 | Transport of Used Oil | CJSMIG-700 | 23 | Arabic services cannot be submitted | Portal team | Portal / launchpad | Framework side.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 1 | Initial page loads with error messages | Reporter + developer | Needs a look | The screenshot is on the ticket; paste it here - Jira is not reachable from where this register is built.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 2 | Applicant details not aligned - should be row wise | Journey developer - Studio config | Config - developer | Design tab.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 3 | Applicant details are duplicated | Journey developer - Studio config | Config - developer | Two fields bound to the same value; hide one.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 4 | Emirates ID search should follow the format; Browse not required | Journey developer - Studio config | Config - developer | PLACEHOLDER + REGEX; FTYPE SEARCH.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 5 | Permit / EID / trade licence order; permit number not a dropdown | Journey developer - Studio config | Config - developer | Design tab + FTYPE.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 6 | Rename the step 'Material Origin source' to 'Batteries/Scrap Details' | Journey developer - Studio config | Config - developer | Step title, EN + AR.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 7 | Fields under Material origin source must be dynamic and mandatory by dropdown value | Journey developer - Studio config | Config - developer | Show/hide belongs in ZRAK_T_JNY_RULE keyed on the dropdown, with REQUIRED on the fields it reveals.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 8 | Vehicle code 1 digit, vehicle plate 4 digits | Journey developer - Studio config | Config - developer | MAX_LEN on both fields.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 9 | 'Materials Det' is duplicated and should be renamed | Journey developer - Studio config | Config - developer | Hide one, rename the other.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 10 | Declaration & Note missing | Journey developer - Studio config | Config - developer | DISPLAY field with a TEXT: default.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 11 | Step 5 request confirmation not required | Journey developer - Studio config | Config - developer | STEP_OFF - the fixpack does this for other journeys and takes one more line.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 12 | Feedback is mandatory | Framework team (us) | Framework - we push | 'Not now' button.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 13 | Attachments are not saving | Reporter + developer | Needs a look | Re-run with &trace=x.
E020 | Batteries / Scrap Handling | CJSMIG-701 | 14 | Vehicle details not saving in the backend | Backend team | Backend / record model | Line the grid spec up against the LIST_SEQUENCE rows for that screen before treating it as a rendering fault.
E023 | Dewatering Approval | CJSMIG-702 | 1 | CJS service Not found | Journey developer - Studio config | Config - developer | The handler class exists and is complete. Check the ZRAK_T_JNY row and the launch URL's journey id - a code that does not resolve gives exactly this.
E025 | Beekeeping Activity | CJSMIG-703 | 1 | Emirates ID search should follow the format; Browse not required | Journey developer - Studio config | Config - developer | PLACEHOLDER + REGEX; FTYPE SEARCH.
E025 | Beekeeping Activity | CJSMIG-703 | 2 | Number of Apiaries max 2 digits; Expected Production max 6 | Journey developer - Studio config | Config - developer | MAX_LEN on both fields.
E025 | Beekeeping Activity | CJSMIG-703 | 3 | Mandatory attachments need the * | Journey developer - Studio config | Config - developer | Tick REQUIRED on each upload field.
E025 | Beekeeping Activity | CJSMIG-703 | 4 | Declaration & Note missing | Journey developer - Studio config | Config - developer | DISPLAY field with a TEXT: default.
E025 | Beekeeping Activity | CJSMIG-703 | 5 | Case id is not correct - shows the wrong number | Reporter + developer | Needs a look | Send the number that was shown next to the case it belongs to. On some families the journey key is not the case id, and the engine has one resolver for that - but it needs the pair to confirm.
E025 | Beekeeping Activity | CJSMIG-703 | 6 | Applicant BP not saved in the record model, not in the backend application | Journey developer - ABAP | Handler class - developer | Fixed. The class called the applicant field OWNER_BP, which is this journey's owner SEARCH BOX; ON_INIT wrote the partner there and blanked it sixteen lines later. Now goes to LOGIN_BP. ZCL_E025_BEEKEEPING_LOGIC.
E026 | Tree Removal / Relocation / Pruning | CJSMIG-704 | 1 | Emirates ID search should follow the format; Browse not required | Journey developer - Studio config | Config - developer | PLACEHOLDER + REGEX; FTYPE SEARCH.
E026 | Tree Removal / Relocation / Pruning | CJSMIG-704 | 2 | Mandatory attachments need the * | Journey developer - Studio config | Config - developer | Tick REQUIRED on each upload field.
E026 | Tree Removal / Relocation / Pruning | CJSMIG-704 | 3 | Declaration & Note missing | Journey developer - Studio config | Config - developer | DISPLAY field with a TEXT: default.
E026 | Tree Removal / Relocation / Pruning | CJSMIG-704 | 4 | Case id is not correct - shows the wrong number | Reporter + developer | Needs a look | Same as E025 - send the pair of numbers.
E026 | Tree Removal / Relocation / Pruning | CJSMIG-704 | 5 | Applicant BP not saved in the record model, not in the backend application | Journey developer - ABAP | Handler class - developer | The applicant partner now also goes out as LOGIN_BP, the field every other journey uses. ZCL_E026_TREE_REMOVAL_LOGIC.

## Framework changes
Framework - made and pushed by the CJS team
Pull and activate. Every 'Overwrite local object' row in the abapGit pull dialog arrives UNTICKED and the ticks reset each time it opens - tick them by hand. ZCL_RAK_JOURNEY_LOGIC and ZCL_RAK_JOURNEY_RENDER first.
Object | What changed | What else it touches | Risk
ZCL_RAK_JOURNEY_ENGINE + ZCL_RAK_JOURNEY_RENDER | NAV_LOCKED( ): once a PAYFEE field on any step holds PAID, or the journey is submitted or closed, Back / the stepper dots / the tab strip stop offering a way back, and the event handler refuses the move even where something was still drawn. | EVERY journey with a fee, in every family - the twelve Municipality journeys that carry RAKPAY included - and every journey at all once it is submitted. | HIGH - a real behaviour change and not opt-in. If any service must let the citizen go back after paying, say so before this is pulled.
ZCL_RAK_JOURNEY_BE | A backend read now SEEDS an editable grid and does not RE-seed one that already holds rows - the citizen's copy wins. GET_BACKEND_TABLE( ) still returns the backend's current answer, so grids served from the store are untouched. | Any family with an editable grid fed by a backend read. Store-fed grids - the LICENSES lists on D003/D004/D011 - are not affected. | MEDIUM - stated cost: a grid the backend re-derives from an EARLIER step's answer no longer refreshes when that answer changes. A handler that needs it to clears the grid itself from ON_CHANGE( ).
ZCL_RAK_JOURNEY_RENDER + ZCL_RAK_JOURNEY_ENGINE | A 'Not now' button beside Send feedback, and FBSKIP behind it, so the closing page always has a way out. | Every journey whose WANTS_FEEDBACK( ) is true - that is the base default, so all of them unless a handler says otherwise. | MEDIUM - feedback becomes skippable everywhere. Deliberate: before this the page had no other exit. If a service must have compulsory feedback, decide now.
ZCL_RAK_JOURNEY_BE | A staged file whose content the store cannot return is counted, named on the trace and reported once on screen as a Warning instead of vanishing. | Every journey - but the code only runs when a file is already being lost. | LOW - inert unless the fault is happening. Adds nothing to a healthy submit.
ZCL_RAK_JOURNEY_RENDER | RENDER_ATTACH( ) passes the native REQUIRED property on the attachment label, so the asterisk actually draws. The old CSS-class marker never reached the DOM. | Every journey with an upload field already marked REQUIRED in ZRAK_T_JNY_FLD. | LOW - visual only, and it follows configuration that is already there. Enforcement was already correct; only the marker was missing.
ZCL_RAK_JOURNEY_LOGIC | DIALOG_FORM( ) repeats the pending messages inside the dialog, so a handler that refuses an OK and keeps the dialog open can be read. | Every popup built through DIALOG_FORM( ) - D001, D004, D006, E016-E018, showcase, test. | LOW - draws nothing when there are no pending messages, so a dialog that opens clean looks exactly as it did.
ZCL_RAK_JOURNEY_LOGIC | DIALOG_FORM( ) gained IV_COLUMNS for two- and three-column dialogs. | Nothing unless a handler asks for it. IV_COLUMNS DEFAULT 1 draws the identical markup the method always drew; only E016/E017/E018 pass 2. | NONE - opt-in per call site.
ZIF_RAK_JOURNEY | MSGS( ) added so a dialog can read the pending messages. | The interface is implemented by ZCL_RAK_JOURNEY_ENGINE and by nothing else, so no other class has to implement anything. | NONE - additive.
ZRAK_CJ_FIXPACK | New report. Applies 19 of the config points mechanically, per journey, idempotent. | Only the journey named on its selection screen. | NONE - new object, nothing calls it.
ZRAK_CJ_BACKUP | New report. Full export and import of one journey's configuration - the fallback before anyone edits config in anger. | Only the journey named on its selection screen. | NONE - new object, nothing calls it.

## Handler code
Handler class fixes - the code, to retype in SE24
These are the journey's OWN class, not the framework. Read it, take it or write your own - it is your service. Where a whole method is given, it is the complete current method: replace the method body with it. Nothing here is pushed for you.
Journey | Ticket | Class | Method / where | What it fixes | Code
E025 | CJSMIG-703 | ZCL_E025_BEEKEEPING_LOGIC | see the code | Applicant BP was written to the owner SEARCH field and then blanked | * --- private section: the constant named the wrong field ------------ * was: constants C_LOGIN_BP type STRING value 'OWNER_BP' ##NO_TEXT. constants C_LOGIN_BP type STRING value 'LOGIN_BP' ##NO_TEXT. * --- ZIF_RAK_JOURNEY_LOGIC~ON_INIT, last line inside the IF ----------- * was: io_ctx->set_val( iv_name = 'OWNER_BP' iv_value = ' ' ). * 'OWNER_BP' is the owner search box (see ON_SEARCH), not the applicant. io_ctx->set_val( iv_name = c_owner_bp iv_value = ' ' ).
E026 | CJSMIG-704 | ZCL_E026_TREE_REMOVAL_LOGIC | see the code | Applicant BP never reached LOGIN_BP | * --- private section: add, leave C_LOGIN_BP exactly as it is --------- constants C_APP_BP type STRING value 'LOGIN_BP' ##NO_TEXT. * --- ZIF_RAK_JOURNEY_LOGIC~ON_INIT, straight after the existing line -- io_ctx->set_val( iv_name = c_login_bp iv_value = ¦{ lv_loginbp }¦ ). io_ctx->set_val( iv_name = c_app_bp iv_value = ¦{ lv_loginbp }¦ ).
E018 | CJSMIG-697 | ZCL_E018_NOC_TRANS_CHEM_LOGIC | see the code | The class had NO ACTIVE VERSION - a string constant does not take an empty literal, so every earlier fix was in the source and none of it was running | * --- private section -------------------------------------------------- * was: constants C_IMPEXP type STRING value ''. <- will not compile constants C_IMPEXP type STRING value IS INITIAL ##NO_TEXT. * Activate the class after this and re-test the whole journey - including the * CX_SY_CONVERSION_NO_NUMBER on post, which may go with it.
E022 | CJSMIG-684 | ZCL_EPDA_E022_DEV_PROJ_LOGIC | METHOD ZIF_RAK_JOURNEY_LOGIC~ON_INIT | Applicant details were written twice on ON_INIT | METHOD zif_rak_journey_logic~on_init. *CALL METHOD SUPER->ZIF_RAK_JOURNEY_LOGIC~ON_INIT * EXPORTING * IO_CTX = * . CALL METHOD super->zif_rak_journey_logic~on_init EXPORTING io_ctx = io_ctx. DATA: lv_loginbp TYPE bu_partner. lv_loginbp = CAST zcl_rak_journey_engine( io_ctx )->mv_loginbp. DATA(lv_rolebp) = CAST zcl_rak_journey_engine( io_ctx )->mv_rolebp. DATA(lv_role) = CAST zcl_rak_journey_engine( io_ctx )->mv_role. "Owner IF lv_loginbp IS NOT INITIAL. NEW zcl_ega_epda_fshry_handler_api( )->get_bp_details( EXPORTING iv_bp_id = lv_loginbp IMPORTING es_bp_details = DATA(ls_bp) ). io_ctx->set_val( iv_name = c_login_bp iv_value = ¦{ lv_loginbp }¦ ). * WRITTEN ONCE. C_PARTNER_NAME is 'APP_NAME' and C_PARTNER_ID is * 'APP_ID', and both were then written a SECOND time below this IF, under * a different language rule - so the two disagreed and the later one won. * The pair below the IF was also outside this guard, so a launch with no * login partner blanked the applicant's name and ID rather than leaving * them alone. * * The rule kept is the one that degrades: an Arabic session with no * Arabic name on the partner record falls back to the English name * rather than showing an empty applicant. io_ctx->set_val( iv_name = c_partner_name iv_value = COND #( WHEN sy-langu <> c_lang_en AND ls_bp-bp_name_ar IS NOT INITIAL THEN CONV string( ls_bp-bp_name_ar ) ELSE CONV string( ls_bp-bp_name ) ) ). io_ctx->set_val( iv_name = c_partner_id iv_value = CONV #( ls_bp-emirates_id ) ). io_ctx->set_val( iv_name = c_partner_mobile iv_value = CONV #( ls_bp-mobile_number ) ). io_ctx->set_val( iv_name = c_partner_email iv_value = CONV #( ls_bp-email_address ) ). io_ctx->set_val( iv_name = c_applicanttype iv_value = ¦{ lv_role }¦ ). ENDIF. ENDMETHOD.
E022 E026 E027 D021 D014gv | CJSMIG-684 / 704 | six classes - see the code | see the code | The applicant's own partner never reached LOGIN_BP, the field every other journey and the record model use. Additive: the existing OWNER_BP write is left alone, so nothing that works today changes | * Applies to ZCL_EPDA_E022_DEV_PROJ_LOGIC, ZCL_E026_TREE_REMOVAL_LOGIC, * ZCL_E027_VICE_CAPTAIN_LOGIC, ZCL_D021_MOD_SCHOOL_FEE_LOGIC and * ZCL_D014_STAFF_GOLD_VISA_LOGIC - all five declare C_LOGIN_BP as 'OWNER_BP'. * E025 is the exception and has its own row above: there OWNER_BP is the owner * SEARCH box, so the constant itself has to be corrected, not added to. * --- private section: ADD this. Leave C_LOGIN_BP exactly as it is. ---- constants C_APP_BP type STRING value 'LOGIN_BP' ##NO_TEXT. * --- ON_INIT: ADD the second line under the existing first one. ------- io_ctx->set_val( iv_name = c_login_bp iv_value = ¦{ lv_loginbp }¦ ). io_ctx->set_val( iv_name = c_app_bp iv_value = ¦{ lv_loginbp }¦ ).
E017 | CJSMIG-687 | ZCL_E017_NOC_EXP_CHEM_LOGIC | METHOD ZIF_RAK_JOURNEY_LOGIC~ON_CUSTOM_VALIDATE | Step 0 refused whenever the role flags disagreed with APPLICANT_ROLE - re-derived now instead of refused | METHOD zif_rak_journey_logic~on_custom_validate. rt = super->zif_rak_journey_logic~on_custom_validate( io_ctx = io_ctx iv_step = iv_step ). CASE iv_step. WHEN 0. * RE-DERIVED, NOT REFUSED. * * PARTNER_OWNER/PARTNER_REP and PERMIT_YES/PERMIT_NO are not answers * in their own right - they are WRITE_FLAGS( )'s projection of * APPLICANT_ROLE and PERMIT_HELD, which are the fields the citizen * actually fills in. This used to refuse the step whenever the role * was set and its flags were not, with "Re-select Owner or * Representative before continuing." * * The citizen had already selected it. WRITE_FLAGS( ) only runs from * ON_CHANGE( ), so any round trip that reinstates the model without * raising a change on APPLICANT_ROLE - a backend read answering the * step, the BP search coming back - leaves the role set and the flags * blank. Re-selecting the same value raises no CHANGE either, so the * one instruction the message gave could not clear it: the journey * stopped at step 1. Reported on all three chemical journeys as * "error showing we u select representative and search with owner EID * details, not moving to next step". * * Rewriting them is what the handler does at post time anyway - * ON_BEFORE_POST( ) calls WRITE_FLAGS( ) before every post - so doing * it here costs nothing and removes the only state that could block. write_flags( io_ctx ). WHEN 2. DATA(ls_grid) = io_ctx->get_grid_data( c_grid ). IF ls_grid-rows IS INITIAL. APPEND VALUE #( type = 'Error' "field = c_grid text = `Add at least one chemical row.` ) TO rt. ENDIF. WHEN OTHERS. ENDCASE. ENDMETHOD.
E017 | CJSMIG-687 | ZCL_E017_NOC_EXP_CHEM_LOGIC | METHOD VALIDATE_INPUT | Add Chemical: all fourteen fields enforced. Ten of the checks were commented out | METHOD validate_input. * ALL FOURTEEN, mirroring the REQUIRED markers in ON_RENDER_POPUP( ). * Ten of these were commented out; CJSMIG-687 Issue 4 settled it. IF io_ctx->get_val( c_hs_pop ) IS INITIAL OR io_ctx->get_val( c_mat_pop ) IS INITIAL OR io_ctx->get_val( c_chem_pop ) IS INITIAL OR io_ctx->get_val( c_cas_no_pop ) IS INITIAL OR io_ctx->get_val( c_chem_form_pop ) IS INITIAL OR io_ctx->get_val( c_packaging_pop ) IS INITIAL OR io_ctx->get_val( c_quantity_pop ) IS INITIAL OR io_ctx->get_val( c_gross_weight_pop ) IS INITIAL OR io_ctx->get_val( c_unit_pop ) IS INITIAL OR io_ctx->get_val( c_bol_pop ) IS INITIAL OR io_ctx->get_val( c_exit_port_pop ) IS INITIAL OR io_ctx->get_val( c_import_pop ) IS INITIAL OR io_ctx->get_val( c_tport_pop ) IS INITIAL. io_ctx->add_msg( iv_type = 'Warning' iv_text = 'Kindly fill required details.' ). * RV_OK stays FALSE. This used to return nothing at all, and ON_POPUP_EVENT * called POPULATE_GRID( ) and CLOSE_POPUP( ) straight afterwards whatever * happened here - so a blank row was added to the grid and the dialog shut, * with only a warning toast to say otherwise. The verdict has to reach the * caller for the message to mean anything. RETURN. ENDIF. rv_ok = abap_true. ENDMETHOD.
E017 | CJSMIG-687 | ZCL_E017_NOC_EXP_CHEM_LOGIC | METHOD ZIF_RAK_JOURNEY_LOGIC~ON_RENDER_POPUP | Add Chemical: the fourteen required markers, and IV_COLUMNS = 2 for the two-column dialog | METHOD zif_rak_journey_logic~on_render_popup. super->zif_rak_journey_logic~on_render_popup( io_ctx = io_ctx io_popup = io_popup iv_id = iv_id ). CASE iv_id. * "On click of ADD Chemical button WHEN c_open_popup. * render_own_popup( io_ctx = io_ctx io_popup = io_popup ). * RETURN. * REQUIRED here is the marker only - DIALOG_FORM( ) sets it on the label * and enforces nothing; a popup's enforcement is the handler's, in * VALIDATE_INPUT( ). So this list has to mirror that method exactly, * and now does: all fourteen marked, all fourteen checked. * * That mirror used to read four and four, with ten lines commented out * in VALIDATE_INPUT( ) and a note here saying the decision had not been * made. It has been now - CJSMIG-687 Issue 4, "all fields should be * mandatory" - so both ends were opened together. Change one end and * the other has to move with it, or the dialog either promises an * asterisk it does not enforce or refuses an OK it never marked. * * THE HISTORY PICKER IS GONE, not commented out: "Use a previous * declaration - field not required" (same ticket). HISTORY_OPTS( ), * HISTORY_APPLY( ) and C_EVT_HIST are deliberately left in place - the * same ticket asks for the legacy Search-from-History screen, which is * a different control reading the same ChemicalHistorySet, and it will * want them. dialog_form( io_ctx = io_ctx io_popup = io_popup iv_title = 'Add Chemical' * Two per row. "Alignment instead each row one filed, can have 2 or * more field for better user experiences" - fourteen fields one to a * row is a dialog nobody can see the bottom of. iv_columns = 2 it_fields = VALUE #( ( name = c_hs_pop label = 'HS Code' required = abap_true placeholder = 'e.g. 2933.99.90' ) ( name = c_mat_pop label = 'Material Name' required = abap_true ) ( name = c_chem_pop label = 'Chemical Name' required = abap_true ) ( name = c_cas_no_pop label = 'CAS Number' maxlen = 20 required = abap_true ) ( name = c_chem_form_pop label = 'Chemical Formula' required = abap_true ) ( name = c_packaging_pop label = 'Packing' required = abap_true ) ( name = c_quantity_pop label = 'Quantity' required = abap_true ) ( name = c_gross_weight_pop label = 'Gross Weight' required = abap_true type = 'Number' ) ( name = c_unit_pop label = 'Unit' required = abap_true type = 'SELECT' options = VALUE #( ( key = 'GAL' text = 'Gallon' ) ( key = 'KG' text = 'Kilogram' ) ( key = 'LIT' text = 'Liter' ) ( key = 'MAT' text = 'Metric Ton' ) ) ) ( name = c_invoice_pop label = 'Invoice Number' required = abap_true ) ( name = c_import_pop label = 'Importing Country' shlp = 'H_T005' required = abap_true ) ( name = c_exit_port_pop label = 'Exit Port' required = abap_true ) ( name = c_bol_pop label = 'Bill of Lading' required = abap_true ) ( name = c_tport_pop label = 'Transport Details' required = abap_true ) ) iv_ok_text = 'Add' iv_ok_evt = c_evt_ownok iv_cxl_evt = c_evt_owncx ). ENDCASE. ENDMETHOD.
E018 | CJSMIG-697 | ZCL_E018_NOC_TRANS_CHEM_LOGIC | METHOD ZIF_RAK_JOURNEY_LOGIC~ON_CUSTOM_VALIDATE | Same role-flag fix as E017 | METHOD zif_rak_journey_logic~on_custom_validate. rt = super->zif_rak_journey_logic~on_custom_validate( io_ctx = io_ctx iv_step = iv_step ). CASE iv_step. WHEN 0. * RE-DERIVED, NOT REFUSED. * * PARTNER_OWNER/PARTNER_REP and PERMIT_YES/PERMIT_NO are not answers * in their own right - they are WRITE_FLAGS( )'s projection of * APPLICANT_ROLE and PERMIT_HELD, which are the fields the citizen * actually fills in. This used to refuse the step whenever the role * was set and its flags were not, with "Re-select Owner or * Representative before continuing." * * The citizen had already selected it. WRITE_FLAGS( ) only runs from * ON_CHANGE( ), so any round trip that reinstates the model without * raising a change on APPLICANT_ROLE - a backend read answering the * step, the BP search coming back - leaves the role set and the flags * blank. Re-selecting the same value raises no CHANGE either, so the * one instruction the message gave could not clear it: the journey * stopped at step 1. Reported on all three chemical journeys as * "error showing we u select representative and search with owner EID * details, not moving to next step". * * Rewriting them is what the handler does at post time anyway - * ON_BEFORE_POST( ) calls WRITE_FLAGS( ) before every post - so doing * it here costs nothing and removes the only state that could block. write_flags( io_ctx ). WHEN 2. DATA(ls_grid) = io_ctx->get_grid_data( c_grid ). IF ls_grid-rows IS INITIAL. APPEND VALUE #( type = 'Error' * field = c_grid text = `Add at least one material row.` ) TO rt. ENDIF. WHEN OTHERS. ENDCASE. ENDMETHOD.
E018 | CJSMIG-697 | ZCL_E018_NOC_TRANS_CHEM_LOGIC | METHOD ZIF_RAK_JOURNEY_LOGIC~ON_RENDER_POPUP | Add Chemical: the fourteen required markers, and IV_COLUMNS = 2 | METHOD zif_rak_journey_logic~on_render_popup. super->zif_rak_journey_logic~on_render_popup( io_ctx = io_ctx io_popup = io_popup iv_id = iv_id ). ** CHECK iv_id = c_pop_mat. CASE iv_id. "c_chem." WHEN 'c_chem1'. * render_own_popup( io_ctx = io_ctx io_popup = io_popup ). * RETURN. WHEN c_chem. "c_evt_details. "c_chem. "c_evt_details. " FOr F4 use this * REQUIRED here is the marker only - DIALOG_FORM( ) sets it on the label * and enforces nothing; a popup's enforcement is the handler's own, in the * OK event. So this list mirrors WHEN c_evt_ownok exactly - now all * fourteen marked and all fourteen tested, per CJSMIG-697 Issue 4 "all * fields should be mandatory". Move one end and the other has to move * with it. dialog_form( io_ctx = io_ctx io_popup = io_popup iv_title = 'Add Chemical' * Two per row. "Alignment instead each row one filed, can have 2 or * more field for better user experiences" - same ticket. iv_columns = 2 it_fields = VALUE #( * The history picker stays out: "Use a previous * declaration - field not required". HISTORY_OPTS( ) * and HISTORY_APPLY( ) are kept for the legacy * Search-from-History screen the same ticket asks * for, which is a different control. ( name = c_hs_code_pop label = 'HS Code' required = abap_true placeholder = 'e.g. 2933.99.90' ) ( name = c_material_name_pop label = 'Material Name' required = abap_true ) ( name = c_chemical_name_pop label = 'Chemical Name' required = abap_true ) ( name = c_cas_pop label = 'CAS Number' maxlen = 20 required = abap_true ) ( name = c_chemical_formula_pop label = 'Chemical Formula' required = abap_true ) ( name = c_packaging_pop label = 'Packing' required = abap_true ) ( name = c_quantity_pop label = 'Quantity' required = abap_true ) ( name = c_gross_weight_pop label = 'Gross Weight' required = abap_true ) ( name = c_uom_pop label = 'UOM' type = 'SELECT' required = abap_true options = VALUE #( ( key = 'GAL' text = 'Gallon' ) ( key = 'KG' text = 'Kilogram' ) ( key = 'LIT' text = 'Liter' ) ( key = 'MAT' text = 'Metric Ton' ) ) ) ( name = c_invoice_pop label = 'Invoice Number' required = abap_true ) ( name = c_origin_pop label = 'Country of Origin' shlp = 'H_T005' required = abap_true ) ( name = c_end_user_pop label = 'Point of Entrance' required = abap_true ) ( name = c_bol_pop label = 'Bill of Lading' required = abap_true ) ( name = c_trans_comp label = 'Transport Company' required = abap_true ) ) iv_ok_text = 'Add' iv_ok_evt = c_evt_ownok iv_cxl_evt = c_evt_owncx ). RETURN. * dialog_form( * io_ctx = io_ctx * io_popup = io_popup * iv_title = 'Add Chemical' * it_fields = VALUE #( * ( name = c_hs_code_pop label = 'HS Code' ) * ( name = c_material_name_pop label = 'Material Name' ) * ( name = c_chemical_name_pop label = 'Chemical Name' ) * ( name = c_cas_pop label = 'CAS Number' ) * ( name = c_chemical_formula_pop label = 'Chemical Formula' ) * ( name = c_packaging_pop label = 'Packing' ) * ( name = c_quantity_pop label = 'Quantity' ) * ( name = c_gross_weight_pop label = 'Gross Weight' ) * ( name = c_uom_pop label = 'UOM' ) * ( name = c_invoice_pop label = 'Invoice Number' ) * ( name = c_origin_pop label = 'Country of Origin' ) * ( name = c_end_user_pop label = 'Point of Entrance' ) * ( name = c_bol_pop label = 'Bill of Lading' ) * ( name = c_trans_comp label = 'Transport Company' ) * ) * iv_ok_text = 'Add' * iv_ok_evt = c_own_add ). WHEN OTHERS. ENDCASE. ENDMETHOD.
E018 | CJSMIG-697 | ZCL_E018_NOC_TRANS_CHEM_LOGIC | METHOD ZIF_RAK_JOURNEY_LOGIC~ON_POPUP_EVENT | Add Chemical: all fourteen enforced on OK, and the dialog stays open when one fails | METHOD zif_rak_journey_logic~on_popup_event. CALL METHOD super->zif_rak_journey_logic~on_popup_event EXPORTING io_ctx = io_ctx iv_id = iv_id iv_event = iv_event. CASE iv_event. WHEN c_evt_details. chem_form_load( io_ctx ). " no id = a new owner io_ctx->open_popup( c_chem ). WHEN c_evt_ownok. "'OWNER_ADD'. " * Nothing here used to check any field - Add saved whatever was typed, * blank fields included. All fourteen are now tested, mirroring the * REQUIRED markers in ON_RENDER_POPUP( ) one for one. IF io_ctx->get_val( c_hs_code_pop ) IS INITIAL OR io_ctx->get_val( c_material_name_pop ) IS INITIAL OR io_ctx->get_val( c_chemical_name_pop ) IS INITIAL OR io_ctx->get_val( c_cas_pop ) IS INITIAL OR io_ctx->get_val( c_chemical_formula_pop ) IS INITIAL OR io_ctx->get_val( c_packaging_pop ) IS INITIAL OR io_ctx->get_val( c_quantity_pop ) IS INITIAL OR io_ctx->get_val( c_gross_weight_pop ) IS INITIAL OR io_ctx->get_val( c_uom_pop ) IS INITIAL OR io_ctx->get_val( c_invoice_pop ) IS INITIAL OR io_ctx->get_val( c_origin_pop ) IS INITIAL OR io_ctx->get_val( c_end_user_pop ) IS INITIAL OR io_ctx->get_val( c_bol_pop ) IS INITIAL OR io_ctx->get_val( c_trans_comp ) IS INITIAL. io_ctx->add_msg( iv_type = 'Warning' iv_text = 'Kindly fill required details.' ). RETURN. ENDIF. own_form_save( io_ctx ). io_ctx->close_popup( ). "Close pop-up screen after adding data * WHEN c_evt_hist. ** Fill the dialog from the chosen declaration and leave it OPEN - this ** shipment's own figures are still to type. * history_apply( io_ctx ). WHEN c_evt_owncx. "'CANCEL'. " io_ctx->close_popup( ). * WHEN c_evt_ownsr. * own_search( io_ctx ). WHEN OTHERS. * "Edit Chemicals Details GRID IF iv_event CP c_edit_pop. own_edit( io_ctx = io_ctx iv_id = substring( val = iv_event off = 9 ) ). io_ctx->open_popup( c_chem ). RETURN. * "Delete data from Chemicals Details GRID ELSEIF iv_event CP c_DELETE_POP. own_delete( io_ctx = io_ctx iv_id = substring( val = iv_event off = 8 ) ). RETURN. ENDIF. ENDCASE. ENDMETHOD.