## Summary
STATUS | Services | What it means | Who moves it
- Excluded (not a service) | 3 | Demonstrably test screens, or a placeholder JOURNEYTYPE value - reason given per row | n/a
1 - In SIT (converted, defects open) | 19 | Converted and running in SIT. 172 observations across the 19 - 24 closed, 148 open | Journey developer + framework team
2 - Built in CJS, not yet in SIT | 29 | Handler class and/or loader exist in git; not yet raised as a SIT ticket | Journey developer
3 - Migrator staged, not yet run | 15 | ZRAK_M_MUNI_LOAD carries the mapping; test run is the default, so nothing is written yet | CJS team - teardown then migrate
4 - Not started | 39 | Present in the /QNV export, no CJS artefact of any kind | Not yet scheduled
TOTAL | 105 | Distinct JOURNEYTYPE service codes in the 43,726-row /QNV/SB_UI_DEFIN export
SOURCES
/QNV/SB_UI_DEFIN export |  | doc/reference/export/QNV_SB_UI_DEFIN.xlsx - 43,726 rows, 201 screen families, parsed for this sheet
SIT ticket register |  | doc/tickets/register.json and SNAPSHOT.md - 19 journeys, 172 observations, as at 5 Sep 2026
Municipality batch |  | src/zrak_m_muni_load.prog.abap - the 15 M-code mapping, read off the JOURNEYTYPE rows
CJS handler classes |  | src/zcl_*_logic.clas.abap - 71 files
CJS loader reports |  | src/zrak_*_load.prog.abap
CJS config exports |  | config/*.cjs1.txt - 4 journeys
CAVEATS
Service names |  | Only names actually written down in this repo are used. A blank one must be read from /QNV/SB_LABELT - never hand-typed or hand-translated.
Three variants per service |  | Each service exists as FAM_n (desktop), MFAM_n (mobile) and NFAM_n (current design). Only the N variant is migrated.
TEN journeys |  | The NMTC / NCTC / NPOA / NCPA JOURNEYTYPE rows are wrong in the export; M030-M035 are mapped by mnemonic and still need confirming.
M015 missing |  | M016 title says Building Regulations / Change of Land Use, but CLU is M015 - a separate service that is not on the batch list.
Converted is not live |  | Every code fix still needs an abapGit Pull AND an activation. Nothing here was compiled or run - there is no SAP connection from this repo.
D014 collision |  | Two handler classes claim D014 - ZCL_D014_STAFF_EXP_CERT_LOGIC and ZCL_D014_STAFF_GOLD_VISA_LOGIC.
The export is the boundary |  | This sheet can only see services defined as ShapeIt screens. Three CJS journeys (AS3, JP1, NOT) are not, and are on the third sheet. A code missing from here is not proof it does not exist - it may simply live elsewhere.
PG01 |  | Was wrongly excluded as payment plumbing in the first version of this sheet. NPAY_1 is a real two-screen citizen flow and is now listed as Not started.
AGAINST YOUR OWN STATUS SHEET
ShapeIt-Migration Status.XLSX - 127 services. Verdict per row on the Reconciliation sheet:
AGREE | 41
CHECK - duplicate code | 1
DISAGREE - no artefact | 15
DISAGREE - not run | 2
NOTE - already staged | 2
NOTE - code not in export | 4
NOTE - not in ShapeIt export | 26
QUALIFY - not tested | 29
QUALIFY - stale load | 7

## Reconciliation
Code | Your description | Dept | Your status | Your remark | Verdict | What the repo and the export actually show | CJS handler in git | CJS loader | In SIT
D001 | D0001 ~ DOK New Lic | DOK | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_D001_SCHOOL_LIC_INIT_LOGIC
D002 | D002~Renewal School License | DOK | Migrated to CJS |  | AGREE | In SIT under CJSMIG-688. Migrated and being tested. | ZCL_D002_SCHOOL_LIC_NEW_LOGIC |  | Yes
D003 | D003~Cancelation School License | DOK | Migrated to CJS |  | AGREE | In SIT under CJSMIG-692. Migrated and being tested. | ZCL_D003_SCHOOL_LIC_RNEW_LOGIC |  | Yes
D004 | Adding/withdrawing a partner(s) | DOK | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_D004_SCHOOL_LIC_AMND_LOGIC
D005 | Changing the school’s name | DOK | Migrated to CJS |  | AGREE | In SIT under CJSMIG-698. Migrated and being tested. | ZCL_D005_SCHOOL_NAME_CHG_LOGIC |  | Yes
D006 | Changing the Manager/Principal | DOK | Migrated to CJS |  | AGREE | In SIT under CJSMIG-696. Migrated and being tested. | ZCL_D006_SCHOOL_MNG_CHG_LOGIC |  | Yes
D007 | Changing the School Curriculum | DOK | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_D007_SCHOOL_CURR_CHG_LOGIC
D008 | Adding/Reducing Grades | DOK | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_D008_SCHOOL_CYCL_CHG_LOGIC
D009 | Changing the school’s Location | DOK | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_D009_SCHOOL_LOCA_CHG_LOGIC | ZRAK_D009_LOAD
D010 | School building Modification | DOK | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_D010_SCHOOL_BULD_CHG_LOGIC
D011 | Advertisement Approval | DOK | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_D011_SCHOOL_ADVERTIS_LOGIC
D012 | School Activities Approvals | DOK | Migrated to CJS |  | AGREE | In SIT under CJSMIG-685. Migrated and being tested. | ZCL_D012_SCHOOL_TRIP_ACT_LOGIC |  | Yes
D013 | Appointment Request for schools Academic/Admin Staff | DOK | Migrated to CJS |  | AGREE | In SIT under CJSMIG-689. Migrated and being tested. | ZCL_D013_STAFF_APP_LET_LOGIC |  | Yes
D014 | Experience Letter Request for School Academic Staff - Schoo | DOK | Migrated to CJS |  | AGREE | In SIT under CJSMIG-690. Migrated and being tested. | ZCL_D014_STAFF_EXP_CERT_LOGIC + ZCL_D014_STAFF_GOLD_VISA_LOGIC (both claim D014) |  | Yes
D015 | Experience Letter Request for School Academic Staff - Teach | DOK | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
D016 | Cancelation of School License | DOK | Migrated to CJS |  | AGREE | In SIT under CJSMIG-694. Migrated and being tested. | ZCL_D016_SCHOOL_LIC_CANC_LOGIC |  | Yes
D019 | School Calendar | DOK | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
D020 | Modify/ Increase school day | DOK | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_D020_MOD_SCHOOL_DAY_LOGIC
D021 | Amendment/Increase of School Fees | DOK | Migrated to CJS |  | AGREE | In SIT under CJSMIG-693. Migrated and being tested. | ZCL_D021_MOD_SCHOOL_FEE_LOGIC |  | Yes
D022 | Pursuing of Study Certificate | DOK | Migrated to CJS |  | AGREE | In SIT under CJSMIG-699. Migrated and being tested. | ZCL_D022_STUD_STUDY_CERT_LOGIC |  | Yes
D023 | Sequential Study Certficate | DOK | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
D024 | Study Leave Certificate | DOK | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_D024_STUD_STUDY_LEAV_LOGIC
D025 | Transfer Certificate | DOK | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_D025_STUD_TRANS_CERT_LOGIC
D026 | Request Transcripts | DOK | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_D026_STUD_REPOR_CARD_LOGIC
D027 | Request for Attestation of Academic Certificate | DOK | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
D028 | Golden Visa for Educator | DOK | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
E001 | E001~New Professional Fishing License - With Boat | EPDA | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
E002 | E002~Renewal Recreational Fishing License with a boat | EPDA | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
E014 | Environmental Consultancy Registration - New | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E014_CONSULT_REG_LOGIC | ZRAK_E014_LOAD
E015 | Environmental Study | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E015_ENV_STUDY_LOGIC | ZRAK_E015_LOAD
E016 | NOC for Import Chemical Products | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E016_NOC_IMP_CHEM_LOGIC
E017 | NOC for Export Chemical Products | EPDA | Migrated to CJS |  | AGREE | In SIT under CJSMIG-687. Migrated and being tested. | ZCL_E017_NOC_EXP_CHEM_LOGIC |  | Yes
E018 | NOC for Transport Chemical Products | EPDA | Migrated to CJS |  | AGREE | In SIT under CJSMIG-697. Migrated and being tested. | ZCL_E018_NOC_TRANS_CHEM_LOGIC |  | Yes
E019 | NOC for Transport Used Oil | EPDA | Migrated to CJS |  | AGREE | In SIT under CJSMIG-700. Migrated and being tested. | ZCL_EPDA_E019_TRANS_USED_LOGIC |  | Yes
E020 | NOC for Transport Batteries/Scrap | EPDA | Migrated to CJS |  | AGREE | In SIT under CJSMIG-701. Migrated and being tested. | ZCL_EPDA_E020_BATT_SCRAP_LOGIC |  | Yes
E021 | NOC for Alternative Fuel | EPDA | Migrated to CJS |  | AGREE | In SIT under CJSMIG-683. Migrated and being tested. | ZCL_EPDA_E021_ALTER_FUEL_LOGIC |  | Yes
E022 | NOC for Development Projects | EPDA | Migrated to CJS |  | AGREE | In SIT under CJSMIG-684. Migrated and being tested. | ZCL_EPDA_E022_DEV_PROJ_LOGIC |  | Yes
E023 | NOC for Dewatering | EPDA | Migrated to CJS |  | AGREE | In SIT under CJSMIG-702. Migrated and being tested. | ZCL_E023_DEWATERING_LOGIC |  | Yes
E024 | Paperworks | EPDA | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
E025 | Honey Beekeeping | EPDA | Migrated to CJS |  | AGREE | In SIT under CJSMIG-703. Migrated and being tested. | ZCL_E025_BEEKEEPING_LOGIC |  | Yes
E026 | NOC for Removal of Trees | EPDA | Migrated to CJS |  | AGREE | In SIT under CJSMIG-704. Migrated and being tested. | ZCL_E026_TREE_REMOVAL_LOGIC |  | Yes
E027 | NOC for Sailing of a Vice Captain | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E027_VICE_CAPTAIN_LOGIC | ZRAK_E027_LOAD
E028 | Renting Berth-Professiona License | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E028_NEW_BERTH_LOGIC (+ ZCL_E028_BERTH_NEW_LOGIC duplicate) | ZRAK_E028_LOAD
E029 | Renting a Store for a professional fisherman | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E029_NEW_STORE_LOGIC | ZRAK_E029_LOAD
E030 | Housing contract for labor (fisherman) | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E030_NEW_HOUSING_LOGIC
E031 | NOC for Outdoor Material Storage for Cement Industries | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E031_MATSTORAGE_LOGIC
E032 | NOC for Drilling groundwater well | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E032_WELLDRILL_LOGIC
E128 | Renting Berth-Professional License-Renew | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E128_RENEW_BERTH_LOGIC
E129 | Renting a Store for a professional fisherman - Renew | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E129_RENEW_STORE_LOGIC
E130 | Housing contract for labor (fisherman) - Renew | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E130_RENEW_HOUSING_LOGIC
E142 | Environmental Consultancy Registration - Renew | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E142_RENEW_CONSULT_LOGIC | ZRAK_E142_LOAD
E146 | Environmental Consultancy Registration - Appeal | EPDA | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_E146_CONSULT_APPEAL_LOGIC | ZRAK_E146_LOAD
EC01 | eComplaint Create | Executive Council | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_RAK_EC01_LOGIC
EC02 | Track eComplaint | Executive Council | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_RAK_EC02_LOGIC
EC03 | Escalate Complaint | Executive Council | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
EC04 | Track Complaint Escalation Request | Executive Council | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
EC05 | eSuggestions Create | Executive Council | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_RAK_EC05_LOGIC
EC06 | eSuggestions Track | Executive Council | Migrated to CJS |  | QUALIFY - not tested | Handler exists in git, but it has never reached SIT. "Migrated" here means built, not verified. It also still needs an abapGit Pull and an activation. | ZCL_RAK_EC06_LOGIC
M011 | M011~Sub division | Municipality | Migrated to CJS |  | QUALIFY - stale load | Migrated, but loaded when PARCEL pointed at FindParcelSet, TITLEDEED at a method name and FLOORUNIT at the wrong set. Needs teardown + re-run before it is fit to show anyone. | ZCL_M011_DIVIDE_LOGIC | ZRAK_M011_LOAD / ZRAK_M_MUNI_LOAD
M012 | M012~Merge | Municipality | Migrated to CJS |  | QUALIFY - stale load | Migrated, but loaded when PARCEL pointed at FindParcelSet, TITLEDEED at a method name and FLOORUNIT at the wrong set. Needs teardown + re-run before it is fit to show anyone. | ZCL_M012_MERGE_LOGIC | ZRAK_M012_LOAD / ZRAK_M_MUNI_LOAD
M013 | M013~Extend Land | Municipality | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
M014 | M014~Rearrangement | Municipality | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
M015 | M015~Change Land Use | Municipality | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
M016 | M016~Change Building Regulations | Municipality | Migrated to CJS |  | QUALIFY - stale load | Migrated, but loaded when PARCEL pointed at FindParcelSet, TITLEDEED at a method name and FLOORUNIT at the wrong set. Needs teardown + re-run before it is fit to show anyone. | ZCL_M016_CBR_LOGIC | ZRAK_M016_LOAD / ZRAK_M_MUNI_LOAD
M017 | M017~Comprehensive Investigation | Municipality | Migrated to CJS |  | QUALIFY - stale load | Migrated, but loaded when PARCEL pointed at FindParcelSet, TITLEDEED at a method name and FLOORUNIT at the wrong set. Needs teardown + re-run before it is fit to show anyone. | ZCL_M017_CI_LOGIC | ZRAK_M017_LOAD / ZRAK_M_MUNI_LOAD
M018 | M018~Obtain Grant | Municipality | Migrated to CJS |  | QUALIFY - stale load | Migrated, but loaded when PARCEL pointed at FindParcelSet, TITLEDEED at a method name and FLOORUNIT at the wrong set. Needs teardown + re-run before it is fit to show anyone. | ZCL_M018_OG_LOGIC | ZRAK_M018_LOAD / ZRAK_M_MUNI_LOAD
M019 | M019~Convert Normal to Program | Municipality | Migrated to CJS |  | QUALIFY - stale load | Migrated, but loaded when PARCEL pointed at FindParcelSet, TITLEDEED at a method name and FLOORUNIT at the wrong set. Needs teardown + re-run before it is fit to show anyone. | ZCL_M019_CPGR_LOGIC | ZRAK_M019_LOAD / ZRAK_M_MUNI_LOAD
M020 | M020~Renew Grant | Municipality | Migrated to CJS |  | QUALIFY - stale load | Migrated, but loaded when PARCEL pointed at FindParcelSet, TITLEDEED at a method name and FLOORUNIT at the wrong set. Needs teardown + re-run before it is fit to show anyone. | ZCL_M020_RGR_LOGIC | ZRAK_M020_LOAD / ZRAK_M_MUNI_LOAD
M021 | M021~Swap Grant | Municipality | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
M022 | M022~Withdraw Grant | Municipality | Migrated to CJS |  | DISAGREE - no artefact | Marked Migrated, but there is NO handler class, loader or config export for it anywhere in git. Either it was built outside this repo, or the row is optimistic.
M028 | M028~Conceptual Design | Municipality | Migrated to CJS |  | DISAGREE - not run | Marked Migrated, but it is in the ZRAK_M_MUNI_LOAD batch and that report has never been run live (test run is the default). Nothing is written to ZRAK_T_JNY* yet. | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD
M029 | M029~Assign Consultant | Municipality | Migrated to CJS |  | DISAGREE - not run | Marked Migrated, but it is in the ZRAK_M_MUNI_LOAD batch and that report has never been run live (test run is the default). Nothing is written to ZRAK_T_JNY* yet. | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD
M030 | M030~New Tenancy Contract | Municipality | To be decided |  | NOTE - already staged | You have it as To be decided, but it is already mapped in ZRAK_M_MUNI_LOAD (family NNTC_1) and would be created by a live run of that report. The mapping is by mnemonic and still needs confirming by whoever owns the TEN screens. | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD
M031 | M031~Modify Tenancy Contract | Municipality | To be decided |  | NOTE - code not in export | The service exists as screen family NMTC_1, but the code M031 appears nowhere in the export - those TEN screens carry wrong JOURNEYTYPE values. This corroborates the mnemonic mapping in ZRAK_M_MUNI_LOAD. | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD
M032 | M032~Renew Tenancy Contract | Municipality | To be decided |  | NOTE - already staged | You have it as To be decided, but it is already mapped in ZRAK_M_MUNI_LOAD (family NRTC_1) and would be created by a live run of that report. The mapping is by mnemonic and still needs confirming by whoever owns the TEN screens. | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD
M033 | M033~Cancel Tenancy Contract | Municipality | To be decided |  | NOTE - code not in export | The service exists as screen family NCTC_1, but the code M033 appears nowhere in the export - those TEN screens carry wrong JOURNEYTYPE values. This corroborates the mnemonic mapping in ZRAK_M_MUNI_LOAD. | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD
M034 | M034~New POA | Municipality | To be decided |  | NOTE - code not in export | The service exists as screen family NPOA_1, but the code M034 appears nowhere in the export - those TEN screens carry wrong JOURNEYTYPE values. This corroborates the mnemonic mapping in ZRAK_M_MUNI_LOAD. | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD
M035 | M035~Cancel POA | Municipality | To be decided |  | NOTE - code not in export | The service exists as screen family NCPA_1, but the code M035 appears nowhere in the export - those TEN screens carry wrong JOURNEYTYPE values. This corroborates the mnemonic mapping in ZRAK_M_MUNI_LOAD. | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD
M041 | M041 ~ OHC Submission | Municipality | To be decided |  | AGREE | Not migrated; nothing in git either.
M042 | M042~Worker Verification | Municipality | To be decided |  | AGREE | Not migrated; nothing in git either.
MC19 | Create Approval of Technical Staff Request | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
MC51 | Online Property Transfer | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
MP00 | MP00~Master Plan | Municipality | To be decided |  | AGREE | Not migrated; nothing in git either.
MP01 | MP01~Pre Concept | Municipality | To be decided |  | AGREE | Not migrated; nothing in git either.
MP02 | MP02~Concept Master Plan | Municipality | To be decided |  | AGREE | Not migrated; nothing in git either.
MP03 | MP03~Final Master Plan | Municipality | To be decided |  | AGREE | Not migrated; nothing in git either.
MP04 | MP04~Master Plan Modification | Municipality | To be decided |  | AGREE | Not migrated; nothing in git either.
MPCA | MPCA~Customer Action | Municipality | To be decided |  | AGREE | Not migrated; nothing in git either.
MPX2 | MPX2~Master Plan Demo 2 | Municipality | To be decided |  | AGREE | Not migrated; nothing in git either.
MPXX | MPXX~Master Plan Demo | Municipality | To be decided |  | AGREE | Not migrated; nothing in git either.
MS56 | Public Health Administration Online Services ZH00 | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
MS87 | Change Engineering Consultant | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
MS88 | Change Building Contractor | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
MS89 | Resolution of Technical Disputes | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
MT63 | Request for testing of public health materilas | Municipality | To be decided |  | AGREE | Not migrated; nothing in git either.
OBA01 | Online Booking Appointment | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
P000 | Case Review | PPD | Not Applicable | Not went Live | AGREE | Not migrated; nothing in git either.
P001 | PPD: Guarantees & Deposits Services | PPD | Not Applicable | Not went Live | AGREE | Not migrated; nothing in git either.
P042 | Appeal Registration | PPD | Not Applicable | Not went Live | AGREE | Not migrated; nothing in git either.
PG01 | Payment Gateway | All | To be decided |  | AGREE | Not migrated; nothing in git either.
PH01 | Issuance of NOC for Public Health Establishments | Municipality | Not Applicable | Free style UI5 | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
PH02 | Approval of a Food Supplier for Educational Institutions | Municipality | Not Applicable | Free style UI5 | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
PH03 | Issuance of a NOC for Handling Non-Halal Food Products | Municipality | Not Applicable | Free style UI5 | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
PH04 | Issuance of a NOC for Disposal of Public Health Waste | Municipality | Not Applicable | Free style UI5 | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
PH05 | Cancellation of a NOC for Handling Non-Halal Food Products | Municipality | Not Applicable | Free style UI5 | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
PH06 | Release of Public Health Products Shipments | Municipality | Not Applicable | Free style UI5 | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
PH07 | Approval of Vehicles for Transport and Distribution of Publi | Municipality | Not Applicable | Free style UI5 | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
PH08 | Site Inspection | Municipality | Not Applicable | Free style UI5 | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
PPPG | PPD Payment Gateway | PPD | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
S001 | Supplier Journey Registration | Finance | Not Applicable | Not went Live and Not in ShapeIt | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
S002 | New Supplier Registration | Finance | Not Applicable | Not went Live and Not in ShapeIt | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
TR01 | Training 1 |  | Demo |  | AGREE | Not migrated; nothing in git either.
US01 | Usarati Report | Municipality |  |  | AGREE | Not migrated; nothing in git either.
Y000 | Y000~Demo Request |  | Demo |  | AGREE | Not migrated; nothing in git either.
E030 | Environmental Permit | EPDA |  |  | CHECK - duplicate code | E030 appears twice on your sheet. Row 46 is "Housing contract for labor (fisherman)", which matches the repo class ZCL_E030_NEW_HOUSING_LOGIC. This row needs a different code. | ZCL_E030_NEW_HOUSING_LOGIC
ZP08 | Building Permit (Existing Buildings) | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
ZP09 | Temporary Building Permit | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
ZP16 | Outside Planting Permit | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
ZP17 | Interlocking Tiles Permit | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
ZP22 | Parking Shade Permit | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
ZS05 | Temporary Connection of Services | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
ZS06 | Completion Certificate | Municipality | To be decided |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
C025 | Marriage Continuity Certificate | COURTS |  |  | NOTE - not in ShapeIt export | This code does not occur anywhere in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, screen name, category or any cell value. Consistent with your own remark where you gave one.
C073 | Power of Attorney | COURTS |  |  | AGREE | Not migrated; nothing in git either.
CA01 | CA01~Customer Action | All | To be decided |  | AGREE | Not migrated; nothing in git either.
D098 | ZBDI_D098 | Not Applicable |  |  | AGREE | Not migrated; nothing in git either.
D099 | Reserved for Tests | Not Applicable |  |  | AGREE | Not migrated; nothing in git either.
IN THE EXPORT, NOT ON YOUR LIST
BA01 |  |  |  |  | MISSING FROM YOUR LIST | This is your OBA01. The export JOURNEYTYPE is BA01; the BAdI class is ZCL_EGA_CJ_ENH_IMPL_OBA01, which is where the O comes from. Same service, two spellings - worth settling on one.
E003 |  |  |  |  | MISSING FROM YOUR LIST | 6 rows, 1 screen family NE003_1, BAdI ZCL_EGA_CJ_ENH_IMPL_E003 registered. A real EPDA service missing from your list.
E011 |  |  |  |  | MISSING FROM YOUR LIST | 1 screen family NE011_1, no BAdI class row. Missing from your list.
M0100 |  |  |  |  | MISSING FROM YOUR LIST | Test rows only (ALA_TEST / TESTH / SCR_TEST). Correctly absent from your list.
MPOA TODO |  |  |  |  | MISSING FROM YOUR LIST | A placeholder JOURNEYTYPE value sitting on NPOA_1, not a service code. Correctly absent.
BUILT IN CJS, ON NEITHER LIST
AS3 | Create Marriage-Take-off Attestation Request (Khula) | COURTS |  |  | MISSING FROM YOUR LIST | Migrated from WebDynpro, lives in src/wd/. Not a ShapeIt screen, so no export row - but it is a delivered CJS journey. | ZCL_C022_KHULA_CERTI_LOGIC | ZRAK_C022_LOAD
JP1 | Judgement Publications | COURTS |  |  | MISSING FROM YOUR LIST | Migrated from WebDynpro ZWDC_ESERV_JUD_PUBL. Read-only search service. src/wd/. | ZCL_C061_JUDGEMENT_PUBL_LOGIC | ZRAK_C061_JUDG_PUBL_LOAD
NOT | Notary Public Declarations | NOTARY |  |  | MISSING FROM YOUR LIST | Backed by an external REST API, hand-authored - the migrator reads /QNV and Notary is not a ShapeIt screen. Test Emirates ID still seeded in DEFAULT_VAL: remove before production. | ZCL_RAK_NOT_APPROVAL_LOGIC | ZRAK_NOT_LOAD
DESCRIPTION CONFLICTS TO SETTLE
D002 |  |  |  |  | CHECK | Your sheet says "Renewal School License". The SIT register calls it "Private School Licence - Apply" and the class is ZCL_D002_SCHOOL_LIC_NEW_LOGIC (new).
D003 |  |  |  |  | CHECK | Your sheet says "Cancelation School License". The SIT register calls it "Private School Licence - Renew" and the class is ZCL_D003_SCHOOL_LIC_RNEW_LOGIC (renew). Cancellation is D016 on both sheets, so D002/D003 look shifted by one somewhere.
D014 / D015 / D028 |  |  |  |  | CHECK | Two handler classes claim D014 - ZCL_D014_STAFF_EXP_CERT_LOGIC and ZCL_D014_STAFF_GOLD_VISA_LOGIC - and it has been an open item for a while. Your sheet resolves it: D028 is "Golden Visa for Educator". The gold-visa class is very likely mis-numbered and belongs to D028, which would leave D015 (Experience Letter - Teacher) with no class at all. Worth checking HANDLER_CLASS on both journeys rather than assuming.
E030 |  |  |  |  | CHECK | Listed twice on your sheet - row 46 "Housing contract for labor (fisherman)" and row 116 "Environmental Permit". The repo class is ZCL_E030_NEW_HOUSING_LOGIC, so row 116 needs a different code.

## ShapeIt inventory
Code | Service name (as recorded in repo) | Category (/QNV) | Legacy screen family (N = current design) | Legacy variants in export | Screens | Export rows | Takes payment | Legacy BAdI / abstract | CJS handler class | CJS loader report | CJS config export | STATUS | SIT ticket | Owner | Notes
D002 | Private School Licence - Apply | DOKSL | ND001_2, ND002_1, ND003_1 | 3 | 12 | 729 |  | ZCL_EGA_CJ_ENH_IMPL_D002, ZCL_EGA_CJ_ENH_IMPL_D001, ZCL_EGA_CJ_ENH_IMPL_E001 | ZCL_D002_SCHOOL_LIC_NEW_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-688 | Hasan Fraz | SIT testing under CJSMIG-688
D003 | Private School Licence - Renew | DOKSL | ND001_3, ND003_1 | 2 | 7 | 362 |  | ZCL_EGA_CJ_ENH_IMPL_D003, ZCL_EGA_CJ_ENH_IMPL_D001, ZCL_EGA_CJ_ENH_IMPL_E001 | ZCL_D003_SCHOOL_LIC_RNEW_LOGIC |  | DOK_D003_SCHOOL_LIC_RENEW.cjs1.txt | 1 - In SIT (converted, defects open) | CJSMIG-692 | anand babu | SIT testing under CJSMIG-692
D005 | Amend - Name Change | DOKSL | ND005_1 | 1 | 4 | 249 |  | ZCL_EGA_CJ_ENH_IMPL_D005 | ZCL_D005_SCHOOL_NAME_CHG_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-698 | Hasan Fraz | SIT testing under CJSMIG-698
D006 | Amend - Manage Change | DOKSL | ND006_1 | 1 | 4 | 243 |  | ZCL_EGA_CJ_ENH_IMPL_D006 | ZCL_D006_SCHOOL_MNG_CHG_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-696 | Hasan Fraz | SIT testing under CJSMIG-696
D012 | School Trips & Activities | DOKSL | ND012_1 | 1 | 4 | 305 |  | ZCL_EGA_CJ_ENH_IMPL_D012 | ZCL_D012_SCHOOL_TRIP_ACT_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-685 | Jyoti Meena | SIT testing under CJSMIG-685
D013 | Staff Appointment Letters | DOKSL | ND013_1 | 1 | 4 | 306 |  | ZCL_EGA_CJ_ENH_IMPL_D012 | ZCL_D013_STAFF_APP_LET_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-689 | Jyoti Meena | SIT testing under CJSMIG-689
D014 | Staff Experience Certificates | DOKSL | ND014_1 | 1 | 1 | 24 |  | ZCL_EGA_CJ_ENH_IMPL_D015 | ZCL_D014_STAFF_EXP_CERT_LOGIC + ZCL_D014_STAFF_GOLD_VISA_LOGIC (both claim D014) |  |  | 1 - In SIT (converted, defects open) | CJSMIG-690 | Jyoti Meena | SIT testing under CJSMIG-690
D016 | Private School Licence - Cancel | DOKSL | ND016_1, ND098_1 | 2 | 8 | 473 |  | ZCL_EGA_CJ_ENH_IMPL_D004, ZCL_EGA_CJ_ENH_IMPL_D012, ZCL_EGA_CJ_ENH_IMPL_D098 | ZCL_D016_SCHOOL_LIC_CANC_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-694 | anand babu | SIT testing under CJSMIG-694
D021 | School Fees (Amend or Increase) | DOKSL | ND021_1 | 1 | 4 | 201 |  | ZCL_EGA_CJ_ENH_IMPL_D004, ZCL_EGA_CJ_ENH_IMPL_D012 | ZCL_D021_MOD_SCHOOL_FEE_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-693 | anand babu | SIT testing under CJSMIG-693
D022 | Pursuing of Study Certificate | DOKSL | ND022_1 | 1 | 3 | 267 | Yes | ZCL_EGA_CJ_ENH_IMPL_D012, ZCL_EGA_CJ_DOK_ABS | ZCL_D022_STUD_STUDY_CERT_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-699 | Hasan Fraz | SIT testing under CJSMIG-699
E017 | Export Chemical Products | EPDA | NE017_1 | 1 | 6 | 314 |  | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_E017_NOC_EXP_CHEM_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-687 | Jyoti Meena | SIT testing under CJSMIG-687
E018 | Transport of Chemical Products | EPDA | NE018_1 | 1 | 5 | 264 |  | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_E018_NOC_TRANS_CHEM_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-697 | Hasan Fraz | SIT testing under CJSMIG-697
E019 | Transport of Used Oil | EPDA | NE019_1 | 1 | 6 | 333 |  | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_EPDA_E019_TRANS_USED_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-700 | anand babu | SIT testing under CJSMIG-700
E020 | Batteries / Scrap Handling | EPDA | NE020_1 | 1 | 6 | 334 |  | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_EPDA_E020_BATT_SCRAP_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-701 | Hasan Fraz | SIT testing under CJSMIG-701
E021 | Alternative Fuel | EPDA | NE021_1 | 1 | 6 | 314 |  | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_EPDA_E021_ALTER_FUEL_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-683 | anand babu | SIT testing under CJSMIG-683
E022 | Development Project | EPDA | NE022_1 | 1 | 5 | 266 |  | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_EPDA_E022_DEV_PROJ_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-684 | anand babu | SIT testing under CJSMIG-684
E023 | Dewatering Approval | EPDA | NE023_1 | 1 | 5 | 286 |  | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_E023_DEWATERING_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-702 | anand babu | SIT testing under CJSMIG-702
E025 | Beekeeping Activity | EPDA | NE025_1 | 1 | 4 | 235 |  | ZCL_EGA_CJ_ENH_IMPL_E025 | ZCL_E025_BEEKEEPING_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-703 | anand babu | SIT testing under CJSMIG-703
E026 | Tree Removal / Relocation / Pruning | EPDA | NE026_1 | 1 | 4 | 234 |  | ZCL_EGA_CJ_ENH_IMPL_E026 | ZCL_E026_TREE_REMOVAL_LOGIC |  |  | 1 - In SIT (converted, defects open) | CJSMIG-704 | anand babu | SIT testing under CJSMIG-704
D001 | School Licence - Initial | DOKSL | ND001_1, NSL_1 | 2 | 7 | 623 | Yes | ZCL_EGA_CJ_ENH_IMPL_D001, ZCL_EGA_CJ_ENH_IMPL_D006 | ZCL_D001_SCHOOL_LIC_INIT_LOGIC |  | DOK_D001_SCHOOL_LIC_INIT.cjs1.txt | 2 - Built in CJS, not yet in SIT |  |  | Handler + loader/config exist in git
D004 | School Licence - Amend | DOKSL | ND004_1 | 1 | 4 | 229 |  | ZCL_EGA_CJ_ENH_IMPL_D004, ZCL_EGA_CJ_ENH_IMPL_D003 | ZCL_D004_SCHOOL_LIC_AMND_LOGIC |  | DOK_D004_SCHOOL_LIC_AMND.cjs1.txt | 2 - Built in CJS, not yet in SIT |  |  | Handler + loader/config exist in git
D007 | School Curriculum Change | DOKSL | ND007_1 | 1 | 4 | 239 |  | ZCL_EGA_CJ_ENH_IMPL_D007 | ZCL_D007_SCHOOL_CURR_CHG_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
D008 | School Cycle Change | DOKSL | ND008_1 | 1 | 4 | 367 |  | ZCL_EGA_CJ_ENH_IMPL_D008 | ZCL_D008_SCHOOL_CYCL_CHG_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
D009 | Changing the school's Location | DOKSL | ND009_1 | 1 | 4 | 265 |  | ZCL_EGA_CJ_ENH_IMPL_D009 | ZCL_D009_SCHOOL_LOCA_CHG_LOGIC | ZRAK_D009_LOAD |  | 2 - Built in CJS, not yet in SIT |  |  | Handler + loader/config exist in git
D010 | School Building Change | DOKSL | ND010_1 | 1 | 4 | 244 |  | ZCL_EGA_CJ_ENH_IMPL_D010 | ZCL_D010_SCHOOL_BULD_CHG_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
D011 | Advertisement Approval | DOKSL | ND011_1 | 1 | 4 | 265 |  | ZCL_EGA_CJ_ENH_IMPL_D011 | ZCL_D011_SCHOOL_ADVERTIS_LOGIC |  | DOK_D011_SCHOOL_ADVERT.cjs1.txt | 2 - Built in CJS, not yet in SIT |  |  | Handler + loader/config exist in git
D020 | Modify School Day | DOKSL | ND020_1 | 1 | 4 | 158 |  | ZCL_EGA_CJ_ENH_IMPL_D004, ZCL_EGA_CJ_ENH_IMPL_D012 | ZCL_D020_MOD_SCHOOL_DAY_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
D024 | Student Study Leave | DOKSL | ND024_1 | 1 | 3 | 267 | Yes | ZCL_EGA_CJ_ENH_IMPL_D012, ZCL_EGA_CJ_DOK_ABS | ZCL_D024_STUD_STUDY_LEAV_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
D025 | Student Transfer Certificate | DOKSL | ND025_1 | 1 | 3 | 267 | Yes | ZCL_EGA_CJ_ENH_IMPL_D012, ZCL_EGA_CJ_DOK_ABS | ZCL_D025_STUD_TRANS_CERT_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
D026 | Student Report Card | DOKSL | ND026_1 | 1 | 3 | 274 | Yes | ZCL_EGA_CJ_ENH_IMPL_D012, ZCL_EGA_CJ_DOK_ABS | ZCL_D026_STUD_REPOR_CARD_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
E014 | Consultancy Registration | EPDA | NE014_1 | 1 | 5 | 428 | Yes | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_E014_CONSULT_REG_LOGIC | ZRAK_E014_LOAD |  | 2 - Built in CJS, not yet in SIT |  |  | Handler + loader/config exist in git
E015 | Environmental Study | EPDA | NE015_1 | 1 | 5 | 392 | Yes | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_E015_ENV_STUDY_LOGIC | ZRAK_E015_LOAD |  | 2 - Built in CJS, not yet in SIT |  |  | Handler + loader/config exist in git
E016 | Import Chemical Products (NOC) | EPDA | NE016_1 | 1 | 5 | 272 |  | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_E016_NOC_IMP_CHEM_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
E027 | Sailing of a Vice Captain | EPDA | NE027_1 | 1 | 5 | 244 |  | ZCL_EGA_CJ_ENH_IMPL_E027 | ZCL_E027_VICE_CAPTAIN_LOGIC | ZRAK_E027_LOAD |  | 2 - Built in CJS, not yet in SIT |  |  | Handler + loader/config exist in git
E028 | Issuance of New Berth Contract | EPDA | NE028_1, NE128_1 | 2 | 8 | 416 |  | ZCL_EGA_CJ_ENH_IMPL_E028, ZCL_EGA_CJ_ENH_IMPL_E128, ZCL_EGA_CJ_FW_RO_EPDA_ABS | ZCL_E028_NEW_BERTH_LOGIC (+ ZCL_E028_BERTH_NEW_LOGIC duplicate) | ZRAK_E028_LOAD |  | 2 - Built in CJS, not yet in SIT |  |  | Handler + loader/config exist in git
E029 | Issuance of New Store Contract | EPDA | NE029_1 | 1 | 4 | 201 |  | ZCL_EGA_CJ_ENH_IMPL_E029 | ZCL_E029_NEW_STORE_LOGIC | ZRAK_E029_LOAD |  | 2 - Built in CJS, not yet in SIT |  |  | Handler + loader/config exist in git
E030 | Issue Housing Contract - Fisherman Labour | EPDA | NE030_1 | 1 | 5 | 293 |  | ZCL_EGA_CJ_FW_RO_EPDA_ABS, ZCL_EGA_CJ_ENH_IMPL_E030 | ZCL_E030_NEW_HOUSING_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
E031 | Material Storage | EPDA | NE031_1 | 1 | 5 | 263 |  | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_E031_MATSTORAGE_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
E032 | Well Drilling | EPDA | NE032_1 | 1 | 5 | 296 |  | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_E032_WELLDRILL_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
E128 | Renew Berth Contract | EPDA | NE128_1 | 1 | 4 | 204 |  | ZCL_EGA_CJ_ENH_IMPL_E128, ZCL_EGA_CJ_FW_RO_EPDA_ABS, ZCL_EGA_CJ_ENH_IMPL_E028 | ZCL_E128_RENEW_BERTH_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
E129 | Renew Store Contract | EPDA | NE129_1 | 1 | 4 | 200 |  | ZCL_EGA_CJ_ENH_IMPL_E129, ZCL_EGA_CJ_FW_RO_EPDA_ABS | ZCL_E129_RENEW_STORE_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
E130 | Renew Housing Contract | EPDA | NE130_1 | 1 | 5 | 283 |  | ZCL_EGA_CJ_ENH_IMPL_E130, ZCL_EGA_CJ_FW_RO_EPDA_ABS | ZCL_E130_RENEW_HOUSING_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
E142 | Renew Consultancy Registration | EPDA | NE014_2 | 1 | 5 | 328 |  | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_E142_RENEW_CONSULT_LOGIC | ZRAK_E142_LOAD |  | 2 - Built in CJS, not yet in SIT |  |  | Handler + loader/config exist in git
E146 | Consultant Appeal | EPDA | NE014_3 | 1 | 5 | 430 | Yes | ZCL_EGA_CJ_CONSULTANT_ABS | ZCL_E146_CONSULT_APPEAL_LOGIC | ZRAK_E146_LOAD |  | 2 - Built in CJS, not yet in SIT |  |  | Handler + loader/config exist in git
EC01 | File Complaint | ECOMP | NEC01_1, NEC05_1 | 2 | 4 | 204 |  | ZCL_EGA_CJ_ENH_IMPL_EC01, ZCL_EGA_CJ_ECOMP_ABS, ZCL_EGA_CJ_ENH_IMPL_EC05 | ZCL_RAK_EC01_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
EC02 | (not recorded in this repo - read from /QNV/SB_LABELT) | ECOMP | NEC02_1 | 1 | 3 | 101 |  | ZCL_EGA_CJ_ENH_IMPL_EC02, ZCL_EGA_CJ_ECOMP_ABS | ZCL_RAK_EC02_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
EC05 | Give Suggestions | ECOMP | NEC05_1 | 1 | 2 | 100 |  | ZCL_EGA_CJ_ENH_IMPL_EC05, ZCL_EGA_CJ_ECOMP_ABS | ZCL_RAK_EC05_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
EC06 | (not recorded in this repo - read from /QNV/SB_LABELT) | ECOMP | NEC06_1 | 1 | 2 | 61 |  | ZCL_EGA_CJ_ENH_IMPL_EC06 | ZCL_RAK_EC06_LOGIC |  |  | 2 - Built in CJS, not yet in SIT |  |  | Handler class exists in git; no loader or config export in this repo
M011 | Request for Plots Division - Ownership | GRANTS, MML, MP | NSUBDIVISION_1, NSUBDIVISION_2 | 8 | 40 | 1843 | Yes |  | ZCL_M011_DIVIDE_LOGIC | ZRAK_M011_LOAD / ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD is TEST-RUN by default; re-run needed - loaded rows carry the old API bindings
M012 | Request for Plots Merger - Ownership | MML, TEST | NMERGE_1, NMERGE_2 | 7 | 36 | 1753 | Yes |  | ZCL_M012_MERGE_LOGIC | ZRAK_M012_LOAD / ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD is TEST-RUN by default; re-run needed - loaded rows carry the old API bindings
M016 | Request for Building Regulations / Change of Land Use - Ownership | COURT, MML, TEN | NCBR_1, NCBR_2, NNTC_1, NRTC_1 | 9 | 57 | 4278 | Yes |  | ZCL_M016_CBR_LOGIC | ZRAK_M016_LOAD / ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD is TEST-RUN by default; re-run needed - loaded rows carry the old API bindings
M017 | Request for a Property Investigation | CI | NCI_1 | 3 | 15 | 683 | Yes |  | ZCL_M017_CI_LOGIC | ZRAK_M017_LOAD / ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD is TEST-RUN by default; re-run needed - loaded rows carry the old API bindings
M018 | Request for a Residential Grant | GRANTS | NOG_1, NOG_2 | 6 | 39 | 2049 | Yes |  | ZCL_M018_OG_LOGIC | ZRAK_M018_LOAD / ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD is TEST-RUN by default; re-run needed - loaded rows carry the old API bindings
M019 | Convert a Valid Grant to a Program Grant Request | FISH_CATG, GRANTS | NCPGR_1, NCPGR_2 | 7 | 36 | 1908 | Yes |  | ZCL_M019_CPGR_LOGIC | ZRAK_M019_LOAD / ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD is TEST-RUN by default; re-run needed - loaded rows carry the old API bindings
M020 | Request to extend grant's validity period | GRANTS | NRGR_1, NRGR_2 | 6 | 33 | 1623 | Yes |  | ZCL_M020_RGR_LOGIC | ZRAK_M020_LOAD / ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD is TEST-RUN by default; re-run needed - loaded rows carry the old API bindings
M028 | Preliminary Design Approval | DML | NCOD_1, NCOD_3 | 6 | 33 | 1658 | Yes |  | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD - generic handler only; the migrator drops PAYFEE, so no pay control yet
M029 | Assign Consultant | DML | NACC_1, NACO_1, NACO_2 | 9 | 27 | 783 |  |  | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD - generic handler only; the migrator drops PAYFEE, so no pay control yet
M030 | New Tenancy Contract | TEN | NCPA_1, NCTC_1, NNTC_1, NPOA_1, NRTC_1 | 5 | 35 | 3799 | Yes |  | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD - generic handler only; the migrator drops PAYFEE, so no pay control yet
M031 | Amend Tenancy Contract | TEN | NMTC_1 | [5 empty] | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD - generic handler only; the migrator drops PAYFEE, so no pay control yet
M032 | Renew Tenancy Contract | TEN | NMTC_1, NRTC_1 | 2 | 12 | 1451 | Yes |  | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD - generic handler only; the migrator drops PAYFEE, so no pay control yet
M033 | Cancel Tenancy Contract | TEN | NCTC_1 | [5 empty] | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD - generic handler only; the migrator drops PAYFEE, so no pay control yet
M034 | Power of Attorney (POA) Request | TEN | NPOA_1 |  |  |  | Yes |  | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD - generic handler only; the migrator drops PAYFEE, so no pay control yet
M035 | Power of Attorney (POA) Cancellation | TEN | NCPA_1 | [5 empty] | ZCL_RAK_JOURNEY_LOGIC (generic) | ZRAK_M_MUNI_LOAD |  | 3 - Migrator staged, not yet run |  |  | ZRAK_M_MUNI_LOAD - generic handler only; the migrator drops PAYFEE, so no pay control yet
BA01 | (not recorded in this repo - read from /QNV/SB_LABELT) | APPOINT | NBA01_1 | 1 | 6 | 327 |  | ZCL_EGA_CJ_ENH_IMPL_OBA01 |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
C073 | (not recorded in this repo - read from /QNV/SB_LABELT) | COURT | NC073_1 | 1 | 6 | 338 | Yes | ZCL_EGA_CJ_COURTS_ABS |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
CA01 | (not recorded in this repo - read from /QNV/SB_LABELT) | CA | NCA | 3 | 3 | 151 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
D015 | (not recorded in this repo - read from /QNV/SB_LABELT) | DOKSL | ND015_1 | 1 | 4 | 281 |  | ZCL_EGA_CJ_ENH_IMPL_D015, ZCL_EGA_CJ_ENH_IMPL_D012 |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
D019 | (not recorded in this repo - read from /QNV/SB_LABELT) | DOKSL | ND019_1 | 1 | 5 | 212 |  | ZCL_EGA_CJ_ENH_IMPL_D004, ZCL_EGA_CJ_ENH_IMPL_D012, ZCL_EGA_CJ_ENH_IMPL_D019 |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
D023 | (not recorded in this repo - read from /QNV/SB_LABELT) | DOKSL | ND023_1 | 1 | 3 | 255 | Yes | ZCL_EGA_CJ_ENH_IMPL_D012, ZCL_EGA_CJ_DOK_ABS |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
D027 | (not recorded in this repo - read from /QNV/SB_LABELT) | DOKSL | ND027_1 | 1 | 2 | 105 |  | ZCL_EGA_CJ_ENH_IMPL_D012 |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
D028 | (not recorded in this repo - read from /QNV/SB_LABELT) | DOKSL | ND028_1 | 1 | 3 | 171 |  | ZCL_EGA_CJ_ENH_IMPL_D028, ZCL_EGA_CJ_ENH_IMPL_D012 |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
D098 | (not recorded in this repo - read from /QNV/SB_LABELT) | DOKSL | ND098_1 | 1 | 4 | 239 |  | ZCL_EGA_CJ_ENH_IMPL_D098 |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
D099 | (not recorded in this repo - read from /QNV/SB_LABELT) | DOKSL | ND099_1 | 1 | 2 | 65 |  | ZCL_EGA_CJ_ENH_IMPL_D099 |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
E001 | (not recorded in this repo - read from /QNV/SB_LABELT) | EPDA | NE001_1 | 2 | 4 | 163 |  | ZCL_EGA_CJ_ENH_IMPL_E001 |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
E002 | (not recorded in this repo - read from /QNV/SB_LABELT) | EPDA | NE002_1 | 1 | 2 | 75 |  | ZCL_EGA_CJ_ENH_IMPL_E002 |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
E003 | (not recorded in this repo - read from /QNV/SB_LABELT) | EPDA | NE003_1 | 1 | 4 | 92 |  | ZCL_EGA_CJ_ENH_IMPL_E003 |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
E011 | (not recorded in this repo - read from /QNV/SB_LABELT) | EPDA | NE011_1 | 1 | 1 | 44 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
E024 | (not recorded in this repo - read from /QNV/SB_LABELT) | EPDA | NE024_1 | 1 | 5 | 251 |  | ZCL_EGA_CJ_CONSULTANT_ABS |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
EC03 | (not recorded in this repo - read from /QNV/SB_LABELT) | ECOMP | NEC03_1 | 1 | 3 | 139 |  | ZCL_EGA_CJ_ENH_IMPL_EC03, ZCL_EGA_CJ_ECOMP_ABS |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
EC04 | (not recorded in this repo - read from /QNV/SB_LABELT) | ECOMP | NEC04_1 | 1 | 3 | 121 |  | ZCL_EGA_CJ_ENH_IMPL_EC04 |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
M013 | (not recorded in this repo - read from /QNV/SB_LABELT) | MML | (legacy-design variants only) | 2 | 13 | 610 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
M014 | (not recorded in this repo - read from /QNV/SB_LABELT) | MML | (legacy-design variants only) | 4 | 26 | 1077 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
M015 | (not recorded in this repo - read from /QNV/SB_LABELT) | MML | (legacy-design variants only) | 2 | 13 | 615 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
M021 | (not recorded in this repo - read from /QNV/SB_LABELT) | GRANTS | (legacy-design variants only) | 4 | 26 | 1073 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
M022 | (not recorded in this repo - read from /QNV/SB_LABELT) | GRANTS | (legacy-design variants only) | 2 | 8 | 207 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
M041 | (not recorded in this repo - read from /QNV/SB_LABELT) | PHD | NIOC_2 | 1 | 2 | 171 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
M042 | (not recorded in this repo - read from /QNV/SB_LABELT) | PHD | NIOC_1 | 1 | 2 | 86 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
MP00 | (not recorded in this repo - read from /QNV/SB_LABELT) | MP | (legacy-design variants only) | 1 | 5 | 329 | Yes |  |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
MP01 | (not recorded in this repo - read from /QNV/SB_LABELT) | MP | (legacy-design variants only) | 2 | 8 | 451 | Yes |  |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
MP02 | (not recorded in this repo - read from /QNV/SB_LABELT) | MP | (legacy-design variants only) | 1 | 7 | 537 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
MP03 | (not recorded in this repo - read from /QNV/SB_LABELT) | MP | (legacy-design variants only) | 1 | 7 | 525 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
MP04 | (not recorded in this repo - read from /QNV/SB_LABELT) | MP | (legacy-design variants only) | 1 | 7 | 476 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
MPCA | (not recorded in this repo - read from /QNV/SB_LABELT) | CA | (legacy-design variants only) | 1 | 1 | 51 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
MPX2 | (not recorded in this repo - read from /QNV/SB_LABELT) | MP | (legacy-design variants only) | 1 | 3 | 156 |  | ZCL_EGA_CJ_ENH_IMPL_MPX2_V1 |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
MPXX | (not recorded in this repo - read from /QNV/SB_LABELT) | MP | (legacy-design variants only) | 1 | 1 | 73 | [5 empty] | 4 - Not started |  |  | MPXX_2 is a single screen, 73 rows - likely a fragment of another MP family rather than a service. Confirm before scheduling.
MT63 | (not recorded in this repo - read from /QNV/SB_LABELT) | PHD | NMT01_1 | 1 | 4 | 215 |  | ZCL_EGA_CJ_PHD_ABS |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
P000 | (not recorded in this repo - read from /QNV/SB_LABELT) | PPD | NP000_1 | 1 | 1 | 26 |  | ZCL_EGA_CJ_PPD_ABS |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
P001 | (not recorded in this repo - read from /QNV/SB_LABELT) | PPD | NP001_1 | 1 | 5 | 351 | Yes | ZCL_EGA_CJ_PPD_ABS |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
P042 | (not recorded in this repo - read from /QNV/SB_LABELT) | ECOMP, PPD | NP042_1 | 2 | 6 | 391 | Yes | ZCL_EGA_CJ_PPD_ABS |  |  |  | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
PG01 | Pay a pending fee (standalone pay + confirm flow) | PAY, TEN | NPAY_1, NRTC_1 | 4 | 18 | 1624 | Yes |  |  |  |  | 4 - Not started |  |  | Standalone pay-a-fee flow (NPAY_1: fee list + pay method + confirmation). CJS has NO equivalent - it puts payment INSIDE each journey via the PAYFEE card and ZCL_RAK_PAY_ENGINE, so a citizen returning later to pay a pending fee has no CJS route. Also appears as a secondary JOURNEYTYPE on NRTC_1.
US01 | (not recorded in this repo - read from /QNV/SB_LABELT) | USAR | NUSAR_1 | 2 | 5 | 181 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
Y000 | (not recorded in this repo - read from /QNV/SB_LABELT) | MP | (legacy-design variants only) | 1 | 2 | 149 | [5 empty] | 4 - Not started |  |  | No CJS handler, loader or config anywhere in this repo
M0100 | (not recorded in this repo - read from /QNV/SB_LABELT) | ALA_TEST, EPDA_CAT, FISH_CATG, FISH_LIC_CATG, FISHING_LICENSE_CATG, TESTH, YF_FISH_CATG | (legacy-design variants only) | 8 | 19 | 1431 | [5 empty] | - Excluded (not a service) |  |  | Test rows - categories ALA_TEST / TESTH / SCR_TEST, no live category
MPOA TODO | (not recorded in this repo - read from /QNV/SB_LABELT) | TEN | NPOA_1 | 1 | 6 | 635 | Yes |  |  |  |  | - Excluded (not a service) |  |  | A placeholder JOURNEYTYPE value on NPOA_1, not a code. That family is M034.
TR01 | (not recorded in this repo - read from /QNV/SB_LABELT) | TEST | (legacy-design variants only) | 1 | 1 | 23 | [5 empty] | - Excluded (not a service) |  |  | TEST_SCREEN, 23 rows - a test screen

## Outside the export
Journey id | Service name | Source platform | CJS handler class | CJS loader | Status | Note
AS3 | Create Marriage-Take-off Attestation Request (Khula) | WebDynpro - Courts | ZCL_C022_KHULA_CERTI_LOGIC | ZRAK_C022_LOAD | 2 - Built in CJS, not yet in SIT | Lives in src/wd/. No /QNV/SB_UI_DEFIN rows exist for it, so it is absent from the inventory sheet by construction.
JP1 | Judgement Publications | WebDynpro ZWDC_ESERV_JUD_PUBL - Courts | ZCL_C061_JUDGEMENT_PUBL_LOGIC | ZRAK_C061_JUDG_PUBL_LOAD | 2 - Built in CJS, not yet in SIT | Read-only search service. Also src/wd/.
NOT | Notary Public Declarations | External REST API (ZCL_RAK_BE_NOT) | ZCL_RAK_NOT_APPROVAL_LOGIC | ZRAK_NOT_LOAD | 2 - Built in CJS, not yet in SIT | Hand-authored - the migrator reads /QNV and Notary is not a ShapeIt screen. Test Emirates ID still seeded in DEFAULT_VAL - remove before production.
PPPG | (raised in review - source unknown) | UNKNOWN |  |  | ? - Cannot be placed | The string PPPG does not occur ANYWHERE in QNV_SB_UI_DEFIN.xlsx - not as a JOURNEYTYPE, a screen name, a category or any cell value across all 43,726 rows. Either it is defined outside ShapeIt (like the three rows above), or it was added after this export was taken on 2 Sep 2026. Tell me where its definition lives and it can be placed.
WHY THIS SHEET EXISTS
The inventory sheet is bounded by one file - the /QNV/SB_UI_DEFIN export. Any service not defined as a ShapeIt screen is invisible to it, however real it is. Three such journeys are already built in CJS. If the list you are checking against is a portal or Jira service list rather than the ShapeIt table, expect more of these.